## Cost Time Optimization 01
Activity | Immediate Predecessors | Immediate Followers | Optimistic (a) |  |  | Most Likely (m) |  |  | Pessimistic (b) |  |  | Coefficient (d) |  |  | Random Duration & Cash
|  |  | Cost | Time | Cost / Time | Cost | Time | Cost / Time | Cost | Time | Cost / Time | Cost | Time | Cost / Time | Risk | Cost | Time | Cost / Time
A | - | C | 350 | 4 | 87.5 | 380 | 5 | 76 | 550 | 10 | 55 | 0.15 | 0.16667 | 0.35385 | 0.97765 | 522.4318 | 9.1811 | 51.0941
B | - | C | 100 | 2 | 50 | 100 | 2.283 | 43.8028 | 150 | 7 | 21.4286 | 0 | 0.056592 | 0.2169 | 0.97765 | 142.5245 | 6.2739 | 17.6484 | Iiteration | Cost | Time | Cost/Time
C | A,B | D,E,G | 256 | 4 | 64 | 256 | 8 | 32 | 400 | 8 | 50 | -1.9737e-16 | 1 | 2.2857 | 0.97765 | 378.4706 | 7.955 | 84.9281 | 1 | 5850.3096 | 90.159 | 825.7553
D | C | H | 52 | 15 | 3.4667 | 52 | 21 | 2.4762 | 105 | 21 | 5 | 0 | 1 | -0.64596 | 0.97765 | 97.076 | 20.9326 | 4.7059 | 2 | 4216.4585 | 60.8408 | 888.1653
E | C | F | 31 | 6 | 5.1667 | 31 | 10 | 3.1 | 63 | 10 | 6.3 | 0 | 1 | -1.8235 | 0.97765 | 58.2157 | 9.955 | 6.0153 | 3 | 6012.0947 | 92.5602 | 847.1556
F | E | H,I | 20 | 6 | 3.3333 | 20 | 8 | 2.5 | 45 | 8 | 5.625 | 0 | 1 | -0.36364 | 0.97765 | 41.2623 | 7.9775 | 5.2249 | 4 | 4018.4914 | 55.6227 | 1115.2097
G | C | H,I | 45 | 7 | 6.4286 | 45 | 12 | 3.75 | 92 | 12 | 7.6667 | 1.5118e-16 | 1 | -2.1635 | 0.97765 | 84.973 | 11.9438 | 7.3374 | 5 | 3914.7043 | 52.5443 | 1071.3429
H | D,F,G | J | 20 | 4 | 5 | 40 | 4 | 10 | 40 | 10 | 4 | 1 | 0 | -5 | 0.97765 | 39.7752 | 9.1029 | 3.6338 | 6 | 4306.1629 | 62.9131 | 907.958
I | G,F | K | 39 | 7 | 5.5714 | 39 | 10 | 3.9 | 85 | 10 | 8.5 | -1.5447e-16 | 1 | -0.57073 | 0.97765 | 78.1226 | 9.9663 | 7.9512 | 7 | 4333.1792 | 63.5121 | 913.4855
J | H | K | 10 | 4 | 2.5 | 10 | 6 | 1.6667 | 21 | 6 | 3.5 | 0 | 1 | -0.83333 | 0.97765 | 19.3554 | 5.9775 | 3.2976 | 8 | 5183.1329 | 79.5395 | 731.1811
K | I,J | - | 25 | 20 | 1.25 | 30 | 20 | 1.5 | 30 | 40 | 0.75 | 1 | 0 | -0.5 | 0.97765 | 29.9438 | 37.0098 | 0.65844 | 9 | 4360.2306 | 64.1022 | 918.8537
Total: |  |  | 948 | 79 | 234.2167 | 1003 | 106.283 | 180.6956 | 1581 | 142 | 167.7702 | 2.15 | 7.2233 | -9.0442 | 10.7541 | 1492.1509 | 136.2755 | 192.4952 | 10 | 4717.4387 | 71.2633 | 657.5522
[19 empty] | 11 | 4826.2297 | 73.2802 | 675.4882
| Cost |  | Time |  | Cost / Time | [13 empty] | 12 | 4696.4791 | 70.8676 | 654.0341
Activity | ES | EF | ES | EF | ES | EF | [12 empty] | 13 | 5315.4192 | 81.7454 | 750.8166
A | 0 | 522.4318 | 0 | 9.1811 | 0 | 51.0941 | [12 empty] | 14 | 4248.0158 | 61.5863 | 895.4118
B | 0 | 142.5245 | 0 | 6.2739 | 0 | 17.6484 | [12 empty] | 15 | 5455.4975 | 84.0236 | 771.1016
C | 664.9563 | 1043.4269 | 9.1811 | 17.1361 | 68.7425 | 153.6706 | [12 empty] | 16 | 4064.2554 | 56.8975 | 1131.0276
D | 1043.4269 | 1140.5029 | 17.1361 | 38.0687 | 153.6706 | 158.3765 | [12 empty] | 17 | 3931.0119 | 53.0524 | 1079.2763
E | 1043.4269 | 1101.6426 | 17.1361 | 27.0912 | 153.6706 | 159.6859 | [12 empty] | 18 | 4984.1342 | 76.1105 | 700.6664
F | 1101.6426 | 1142.9049 | 27.0912 | 35.0687 | 159.6859 | 164.9108 | [12 empty] | 19 | 4043.5023 | 56.324 | 1124.0488
G | 1043.4269 | 1128.4 | 17.1361 | 29.0799 | 153.6706 | 161.0081 | [12 empty] | 20 | 5823.067 | 89.7484 | 822.0965
H | 3411.8078 | 3451.583 | 38.0687 | 47.1716 | 484.2954 | 487.9292 | [12 empty] | 21 | 4028.6813 | 55.9098 | 1118.8714
I | 2271.3049 | 2349.4274 | 35.0687 | 45.035 | 325.9189 | 333.8701 | [12 empty] | 22 | 4159.7249 | 59.4435 | 1159.6718
J | 3451.583 | 3470.9384 | 47.1716 | 53.1492 | 487.9292 | 491.2268 | [12 empty] | 23 | 5268.3831 | 80.9673 | 743.8903
K | 5820.3658 | 5850.3096 | 53.1492 | 90.159 | 825.0969 | 825.7553 | [12 empty] | 24 | 4021.6499 | 55.7119 | 1116.354
[19 empty] | 25 | 4722.7624 | 71.3634 | 658.4424
| Target Risk: |  | 10.7541 | [15 empty] | 26 | 5565.826 | 85.7791 | 786.7361
| Target Cost: |  | 5850.3096 | [15 empty] | 27 | 4393.6672 | 64.8195 | 925.2803
| Target Time: |  | 90.159 | [15 empty] | 28 | 4517.1202 | 67.3706 | 622.9478
| Target Cost/Time: |  | 825.7553 | [15 empty] | 29 | 4309.9095 | 62.9968 | 908.7351
[19 empty] | 30 | 5822.1775 | 89.7349 | 821.9768
[19 empty] | 31 | 4580.5307 | 68.6316 | 634.1556
[19 empty] | 32 | 3995.3814 | 54.9636 | 1106.5642
[19 empty] | 33 | 4826.8222 | 73.291 | 675.5845
[19 empty] | 34 | 3966.5426 | 54.123 | 1095.0067
[19 empty] | 35 | 4132.8377 | 58.7482 | 1152.1975
[19 empty] | 36 | 4177.9821 | 59.9023 | 1164.4535
[19 empty] | 37 | 4786.6436 | 72.5531 | 669.0222
[19 empty] | 38 | 5514.186 | 84.9616 | 779.4546
[19 empty] | 39 | 4976.0611 | 75.9683 | 699.4012
[19 empty] | 40 | 5213.3966 | 80.0491 | 735.7163
[19 empty] | 41 | 4602.9002 | 69.0697 | 638.0493
[19 empty] | 42 | 4173.116 | 59.7809 | 1163.2002
[19 empty] | 43 | 4061.5526 | 56.8232 | 1130.1356
[19 empty] | 44 | 5528.3805 | 85.187 | 781.4624
[19 empty] | 45 | 4690.1326 | 70.7474 | 652.9645
[19 empty] | 46 | 4823.4288 | 73.229 | 675.0329
[19 empty] | 47 | 3901.8811 | 52.1354 | 1064.7019
[19 empty] | 48 | 4883.1331 | 74.3125 | 684.6704
[19 empty] | 49 | 4380.1421 | 64.5309 | 922.7072
[19 empty] | 50 | 3999.5109 | 55.0822 | 1108.1461
[19 empty] | 51 | 4633.1705 | 69.6572 | 643.2719
[19 empty] | 52 | 5365.9286 | 82.5734 | 758.1889
[19 empty] | 53 | 4804.6157 | 72.8841 | 671.966
[19 empty] | 54 | 4216.413 | 60.8397 | 888.1546
[19 empty] | 55 | 4510.5779 | 67.2388 | 621.7761
[19 empty] | 56 | 4398.2119 | 64.916 | 601.1378
[19 empty] | 57 | 4614.5974 | 69.2974 | 640.0736
[19 empty] | 58 | 4046.6778 | 56.4122 | 1125.1364
[19 empty] | 59 | 4428.6958 | 65.5579 | 606.8404
[19 empty] | 60 | 4342.5615 | 63.7178 | 915.3654
[19 empty] | 61 | 4875.5723 | 74.1761 | 683.4578
[19 empty] | 62 | 4485.2664 | 66.7254 | 617.2143
[19 empty] | 63 | 4308.9503 | 62.9754 | 908.5365
[19 empty] | 64 | 4461.186 | 66.232 | 612.8298
[19 empty] | 65 | 5615.3187 | 86.556 | 793.656
[19 empty] | 66 | 4628.9056 | 69.5747 | 642.5392
[19 empty] | 67 | 4568.685 | 68.3983 | 632.0815
[19 empty] | 68 | 4205.5189 | 60.5775 | 1171.2809
[19 empty] | 69 | 5624.0889 | 86.693 | 794.8763
[19 empty] | 70 | 4289.1872 | 62.5314 | 904.3922
[19 empty] | 71 | 4983.6248 | 76.1015 | 700.5866
[19 empty] | 72 | 4931.4696 | 75.1782 | 692.372
[19 empty] | 73 | 4360.7845 | 64.1142 | 918.962
[19 empty] | 74 | 4061.4738 | 56.821 | 1130.1095
[19 empty] | 75 | 5440.9283 | 83.7893 | 769.0149
[19 empty] | 76 | 4402.0786 | 64.9979 | 601.8658
[19 empty] | 77 | 5288.8771 | 81.3072 | 746.9154
[19 empty] | 78 | 4812.9422 | 73.037 | 673.3252
[19 empty] | 79 | 4435.2465 | 65.6946 | 608.0551
[19 empty] | 80 | 4647.6147 | 69.9354 | 645.746
[19 empty] | 81 | 4717.9136 | 71.2723 | 657.6317
[19 empty] | 82 | 4970.5897 | 75.8718 | 698.5425
[19 empty] | 83 | 5753.6713 | 88.6941 | 812.7031
[19 empty] | 84 | 4285.7854 | 62.4543 | 903.6685
[19 empty] | 85 | 5069.048 | 77.5911 | 713.8403
[19 empty] | 86 | 4672.433 | 70.4107 | 649.9709
[19 empty] | 87 | 4334.0412 | 63.531 | 913.659
[19 empty] | 88 | 4130.0311 | 58.674 | 1151.3842
[19 empty] | 89 | 4388.9389 | 64.7188 | 924.3847
[19 empty] | 90 | 3925.3696 | 52.878 | 1076.5901
[19 empty] | 91 | 4742.8579 | 71.74 | 661.7907
[19 empty] | 92 | 5195.5208 | 79.7485 | 733.0407
[19 empty] | 93 | 4826.1242 | 73.2782 | 675.4711
[19 empty] | 94 | 4190.2041 | 60.2043 | 1167.5375
[19 empty] | 95 | 4331.2739 | 63.4702 | 913.1013
[19 empty] | 96 | 4957.9277 | 75.648 | 696.5513
[19 empty] | 97 | 4685.5119 | 70.6596 | 652.1845
[19 empty] | 98 | 4083.3641 | 57.4197 | 1137.2001
[19 empty] | 99 | 4666.2439 | 70.2925 | 648.9203
[19 empty] | 100 | 5119.548 | 78.4591 | 721.5651
[19 empty] | 101 | 5290.3622 | 81.3317 | 747.1342
[19 empty] | 102 | 5762.8721 | 88.8346 | 813.9546
[19 empty] | 103 | 4870.5269 | 74.085 | 682.6473
[19 empty] | 104 | 4513.4122 | 67.2959 | 622.2841
[19 empty] | 105 | 5006.7712 | 76.5079 | 704.2019
[19 empty] | 106 | 4436.4974 | 65.7207 | 608.2866
[19 empty] | 107 | 4871.0322 | 74.0942 | 682.7285
[19 empty] | 108 | 5299.2674 | 81.4789 | 748.4448
[19 empty] | 109 | 5480.115 | 84.4182 | 774.6155
[19 empty] | 110 | 5799.8351 | 89.3968 | 818.9636
[19 empty] | 111 | 5225.3495 | 80.2495 | 737.5004
[19 empty] | 112 | 4109.2369 | 58.1185 | 1145.2098
[19 empty] | 113 | 4913.6442 | 74.8601 | 689.542
[19 empty] | 114 | 4366.2266 | 64.2318 | 920.0225
[19 empty] | 115 | 4469.0325 | 66.3933 | 614.2634
[19 empty] | 116 | 4718.2991 | 71.2795 | 657.6962
[19 empty] | 117 | 4737.6383 | 71.6424 | 660.9229
[19 empty] | 118 | 3922.8663 | 52.8002 | 1075.3791
[19 empty] | 119 | 5116.4574 | 78.4062 | 721.0946
[19 empty] | 120 | 4058.5724 | 56.7411 | 1129.1463
[19 empty] | 121 | 3972.502 | 54.2985 | 1097.4734
[19 empty] | 122 | 4359.8996 | 64.095 | 918.789
[19 empty] | 123 | 4561.4771 | 68.2558 | 630.8151
[19 empty] | 124 | 4924.9253 | 75.0616 | 691.3343
[19 empty] | 125 | 4352.4053 | 63.9324 | 917.317
[19 empty] | 126 | 4389.026 | 64.7207 | 924.4012
[19 empty] | 127 | 5103.4217 | 78.1829 | 719.1069
[19 empty] | 128 | 4314.1661 | 63.0916 | 909.6137
[19 empty] | 129 | 4432.5292 | 65.6379 | 607.5516
[19 empty] | 130 | 4468.3691 | 66.3797 | 614.1423
[19 empty] | 131 | 5612.5962 | 86.5135 | 793.2768
[19 empty] | 132 | 4256.4205 | 61.7816 | 897.286
[19 empty] | 133 | 4850.1345 | 73.7156 | 679.3614
[19 empty] | 134 | 5247.1019 | 80.6131 | 740.7367
[19 empty] | 135 | 4073.9972 | 57.1644 | 1134.2032
[19 empty] | 136 | 4287.7466 | 62.4988 | 904.0861
[19 empty] | 137 | 4379.8086 | 64.5237 | 922.6433
[19 empty] | 138 | 4837.6769 | 73.489 | 677.3459
[19 empty] | 139 | 4740.3296 | 71.6927 | 661.3705
[19 empty] | 140 | 4649.4081 | 69.9699 | 646.0523
[19 empty] | 141 | 4992.6886 | 76.2609 | 702.0045
[19 empty] | 142 | 5728.5326 | 88.3093 | 809.2742
[19 empty] | 143 | 5241.2676 | 80.5157 | 739.87
[19 empty] | 144 | 5251.0258 | 80.6785 | 741.3191
[19 empty] | 145 | 5359.581 | 82.4698 | 757.2661
[19 empty] | 146 | 4675.2951 | 70.4652 | 650.4561
[19 empty] | 147 | 4341.7937 | 63.701 | 915.2123
[19 empty] | 148 | 4597.4801 | 68.9638 | 637.1086
[19 empty] | 149 | 4778.5181 | 72.403 | 667.6867
[19 empty] | 150 | 4415.9828 | 65.2913 | 604.4724
[19 empty] | 151 | 4540.4635 | 67.8383 | 627.1043
[19 empty] | 152 | 4660.2614 | 70.1781 | 647.9029
[19 empty] | 153 | 4396.5911 | 64.8816 | 600.8322
[19 empty] | 154 | 4725.1052 | 71.4074 | 658.8338
[19 empty] | 155 | 4210.0141 | 60.686 | 1172.3557
[19 empty] | 156 | 4936.6602 | 75.2706 | 693.1939
[19 empty] | 157 | 4637.6051 | 69.7427 | 644.0327
[19 empty] | 158 | 4386.1159 | 64.6586 | 923.848
[19 empty] | 159 | 4517.1872 | 67.372 | 622.9598
[19 empty] | 160 | 4324.2372 | 63.3149 | 911.6752
[19 empty] | 161 | 3971.9671 | 54.2828 | 1097.2538
[19 empty] | 162 | 4906.3603 | 74.7297 | 688.3822
[19 empty] | 163 | 4246.1816 | 61.5435 | 894.9998
[19 empty] | 164 | 4513.3524 | 67.2947 | 622.2734
[19 empty] | 165 | 4056.4766 | 56.6833 | 1128.4469
[19 empty] | 166 | 5601.1581 | 86.3344 | 791.6819
[19 empty] | 167 | 5104.8158 | 78.2068 | 719.3198
[19 empty] | 168 | 3984.6245 | 54.6526 | 1102.3615
[19 empty] | 169 | 5472.3601 | 84.2941 | 773.5102
[19 empty] | 170 | 4159.6983 | 59.4428 | 1159.6647
[19 empty] | 171 | 5176.6189 | 79.4295 | 730.2015
[19 empty] | 172 | 3902.66 | 52.1605 | 1065.1167
[19 empty] | 173 | 5086.4603 | 77.8914 | 716.5128
[19 empty] | 174 | 4125.5763 | 58.5554 | 1150.0804
[19 empty] | 175 | 4153.5366 | 59.2858 | 1157.9997
[19 empty] | 176 | 4311.6074 | 63.0346 | 909.0861
[19 empty] | 177 | 4363.7498 | 64.1783 | 919.5406
[19 empty] | 178 | 4953.3747 | 75.5674 | 695.8339
[19 empty] | 179 | 4838.5585 | 73.5051 | 677.4887
[19 empty] | 180 | 5207.9788 | 79.9581 | 734.9064
[19 empty] | 181 | 4123.0721 | 58.4887 | 1149.3429
[19 empty] | 182 | 5141.6328 | 78.8359 | 724.9187
[19 empty] | 183 | 4474.7507 | 66.5106 | 615.3051
[19 empty] | 184 | 5665.3586 | 87.335 | 800.5949
[19 empty] | 185 | 4218.0423 | 60.8787 | 888.5374
[19 empty] | 186 | 4981.1585 | 76.0581 | 700.2003
[19 empty] | 187 | 5654.6253 | 87.1685 | 799.1114
[19 empty] | 188 | 4898.8368 | 74.5948 | 687.1822
[19 empty] | 189 | 5035.0544 | 77.0016 | 708.5949
[19 empty] | 190 | 4170.6402 | 59.7189 | 1162.5568
[19 empty] | 191 | 4303.3234 | 62.8496 | 907.3667
[19 empty] | 192 | 4385.4101 | 64.6435 | 923.7136
[19 empty] | 193 | 4715.878 | 71.2339 | 657.291
[19 empty] | 194 | 4294.101 | 62.6423 | 905.4321
[19 empty] | 195 | 4436.9634 | 65.7304 | 608.3728
[19 empty] | 196 | 4735.2534 | 71.5977 | 660.5259
[19 empty] | 197 | 4645.5069 | 69.8949 | 645.3856
[19 empty] | 198 | 4544.6837 | 67.9224 | 627.8519
[19 empty] | 199 | 4129.3903 | 58.657 | 1151.1975
[19 empty] | 200 | 5383.2821 | 82.8562 | 760.7065
[19 empty] | 201 | 4008.2228 | 55.3313 | 1111.4293
[19 empty] | 202 | 5289.3016 | 81.3142 | 746.978
[19 empty] | 203 | 4281.1737 | 62.3496 | 902.6824
[19 empty] | 204 | 4029.1179 | 55.9221 | 1119.0264
[19 empty] | 205 | 6128.7957 | 94.2532 | 862.2477
[19 empty] | 206 | 4100.9412 | 57.8954 | 1142.6828
[19 empty] | 207 | 3989.5514 | 54.7954 | 1104.3015
[19 empty] | 208 | 4211.908 | 60.7316 | 1172.8054
[19 empty] | 209 | 5007.3512 | 76.518 | 704.2922
[19 empty] | 210 | 5423.9673 | 83.5157 | 766.579
[19 empty] | 211 | 4327.7597 | 63.3927 | 912.3905
[19 empty] | 212 | 4458.6837 | 66.1804 | 612.3715
[19 empty] | 213 | 5543.9755 | 85.4341 | 783.6628
[19 empty] | 214 | 4147.5612 | 59.1323 | 1156.3587
[19 empty] | 215 | 4688.1098 | 70.709 | 652.6232
[19 empty] | 216 | 4074.007 | 57.1646 | 1134.2063
[19 empty] | 217 | 4388.9332 | 64.7187 | 924.3836
[19 empty] | 218 | 4867.9665 | 74.0387 | 682.2356
[19 empty] | 219 | 4445.1562 | 65.9006 | 609.8857
[19 empty] | 220 | 6094.3857 | 93.7574 | 857.8275
[19 empty] | 221 | 4094.221 | 57.714 | 1140.6076
[19 empty] | 222 | 4956.7446 | 75.627 | 696.3649
[19 empty] | 223 | 4042.1483 | 56.2863 | 1123.5828
[19 empty] | 224 | 4978.9406 | 76.0191 | 699.8527
[19 empty] | 225 | 4570.3854 | 68.4318 | 632.3797
[19 empty] | 226 | 5062.1873 | 77.4724 | 712.7847
[19 empty] | 227 | 5392.7528 | 83.0101 | 762.0773
[19 empty] | 228 | 4398.585 | 64.9239 | 601.2081
[19 empty] | 229 | 4459.6076 | 66.1995 | 612.5408
[19 empty] | 230 | 4840.2381 | 73.5357 | 677.7607
[19 empty] | 231 | 4380.1337 | 64.5307 | 922.7056
[19 empty] | 232 | 5556.9038 | 85.6384 | 785.4825
[19 empty] | 233 | 5350.5402 | 82.3219 | 755.9499
[19 empty] | 234 | 4571.0351 | 68.4447 | 632.4936
[19 empty] | 235 | 4408.8913 | 65.142 | 603.1452
[19 empty] | 236 | 5604.1376 | 86.3811 | 792.0976
[19 empty] | 237 | 4767.02 | 72.1899 | 665.7919
[19 empty] | 238 | 4015.4982 | 55.538 | 1114.1174
[19 empty] | 239 | 4248.3 | 61.5929 | 895.4755
[19 empty] | 240 | 4324.9014 | 63.3296 | 911.8103
[19 empty] | 241 | 3974.6461 | 54.3614 | 1098.3503
[19 empty] | 242 | 4546.8508 | 67.9656 | 628.2353
[19 empty] | 243 | 4278.2858 | 62.2839 | 902.0619
[19 empty] | 244 | 4339.5008 | 63.6508 | 914.7543
[19 empty] | 245 | 4627.944 | 69.5561 | 642.3738
[19 empty] | 246 | 4755.8713 | 71.9827 | 663.949
[19 empty] | 247 | 4617.9346 | 69.3622 | 640.6497
[19 empty] | 248 | 4676.4663 | 70.4875 | 650.6545
[19 empty] | 249 | 4872.343 | 74.1178 | 682.9391
[19 empty] | 250 | 4275.1221 | 62.2117 | 901.3795
[19 empty] | 251 | 4496.0708 | 66.9452 | 619.1673
[19 empty] | 252 | 4373.0434 | 64.3786 | 921.3425
[19 empty] | 253 | 4117.2823 | 58.3341 | 1147.6254
[19 empty] | 254 | 4693.0426 | 70.8025 | 653.4552
[19 empty] | 255 | 4291.8405 | 62.5913 | 904.9545
[19 empty] | 256 | 4924.2359 | 75.0493 | 691.225
[19 empty] | 257 | 3897.2683 | 51.9859 | 1062.2123
[19 empty] | 258 | 4493.3467 | 66.8899 | 618.6757
[19 empty] | 259 | 4169.5894 | 59.6926 | 1162.2825
[19 empty] | 260 | 5617.4343 | 86.5891 | 793.9505
[19 empty] | 261 | 4801.0131 | 72.8179 | 671.377
[19 empty] | 262 | 4581.7531 | 68.6557 | 634.3692
[19 empty] | 263 | 3999.5065 | 55.0821 | 1108.1444
[19 empty] | 264 | 4745.7816 | 71.7946 | 662.2763
[19 empty] | 265 | 4102.158 | 57.9282 | 1143.0558
[19 empty] | 266 | 4872.8164 | 74.1264 | 683.0152
[19 empty] | 267 | 5213.9442 | 80.0583 | 735.7982
[19 empty] | 268 | 4269.2345 | 62.0769 | 900.1018
[19 empty] | 269 | 4349.6849 | 63.8732 | 916.7798
[19 empty] | 270 | 4627.4364 | 69.5463 | 642.2865
[19 empty] | 271 | 4500.675 | 67.0386 | 619.9969
[19 empty] | 272 | 5599.543 | 86.3091 | 791.4564
[19 empty] | 273 | 4074.8044 | 57.1864 | 1134.4636
[19 empty] | 274 | 4983.8083 | 76.1048 | 700.6153
[19 empty] | 275 | 4525.7879 | 67.5448 | 624.4955
[19 empty] | 276 | 4352.7848 | 63.9407 | 917.3919
[19 empty] | 277 | 4272.5956 | 62.1539 | 900.8324
[19 empty] | 278 | 5038.5142 | 77.0618 | 709.1305
[19 empty] | 279 | 4818.7897 | 73.1441 | 674.278
[19 empty] | 280 | 4130.4542 | 58.6852 | 1151.5072
[19 empty] | 281 | 4059.6131 | 56.7698 | 1129.4924
[19 empty] | 282 | 4292.0009 | 62.5949 | 904.9884
[19 empty] | 283 | 5416.177 | 83.3898 | 765.4578
[19 empty] | 284 | 4921.3981 | 74.9986 | 690.7744
[19 empty] | 285 | 4274.2246 | 62.1912 | 901.1853
[19 empty] | 286 | 5388.7417 | 82.945 | 761.497
[19 empty] | 287 | 4682.0259 | 70.5934 | 651.5954
[19 empty] | 288 | 4263.4442 | 61.9438 | 898.8355
[19 empty] | 289 | 4516.0496 | 67.3491 | 622.7563
[19 empty] | 290 | 4591.4829 | 68.8465 | 636.0657
[19 empty] | 291 | 4078.9917 | 57.3007 | 1135.8079
[19 empty] | 292 | 5105.8075 | 78.2238 | 719.4711
[19 empty] | 293 | 4226.4269 | 61.0785 | 890.4918
[19 empty] | 294 | 4600.0566 | 69.0142 | 637.5559
[19 empty] | 295 | 5341.1697 | 82.1685 | 754.5834
[19 empty] | 296 | 5159.6461 | 79.142 | 727.6431
[19 empty] | 297 | 5908.3129 | 91.0272 | 833.4921
[19 empty] | 298 | 5688.664 | 87.6956 | 803.8072
[19 empty] | 299 | 4129.1717 | 58.6511 | 1151.1337
[19 empty] | 300 | 5548.4792 | 85.5053 | 784.2971
[19 empty] | 301 | 4453.741 | 66.0784 | 611.465
[19 empty] | 302 | 5219.6216 | 80.1535 | 736.646
[19 empty] | 303 | 5228.4286 | 80.3011 | 737.9593
[19 empty] | 304 | 4151.8381 | 59.2423 | 1157.5359
[19 empty] | 305 | 5159.1349 | 79.1334 | 727.566
[19 empty] | 306 | 4700.4779 | 70.9433 | 654.7069
[19 empty] | 307 | 4152.386 | 59.2563 | 1157.6858
[19 empty] | 308 | 5397.6559 | 83.0897 | 762.786
[19 empty] | 309 | 5173.9397 | 79.3842 | 729.7982
[19 empty] | 310 | 4856.6753 | 73.8343 | 680.4171
[19 empty] | 311 | 4305.0656 | 62.8886 | 907.7297
[19 empty] | 312 | 5249.2982 | 80.6497 | 741.0628
[19 empty] | 313 | 4607.1718 | 69.1529 | 638.7894
[19 empty] | 314 | 4458.0565 | 66.1675 | 612.2566
[19 empty] | 315 | 4778.2907 | 72.3988 | 667.6493
[19 empty] | 316 | 5105.9064 | 78.2255 | 719.4862
[19 empty] | 317 | 5421.495 | 83.4758 | 766.2234
[19 empty] | 318 | 5670.4694 | 87.4142 | 801.3004
[19 empty] | 319 | 4136.1334 | 58.835 | 1153.1442
[19 empty] | 320 | 4813.6042 | 73.0491 | 673.4332
[19 empty] | 321 | 3977.757 | 54.4525 | 1099.6131
[19 empty] | 322 | 4565.9774 | 68.3448 | 631.6061
[19 empty] | 323 | 5572.7202 | 85.8877 | 787.7034
[19 empty] | 324 | 4230.437 | 61.1735 | 891.4177
[19 empty] | 325 | 5003.6943 | 76.454 | 703.7223
[19 empty] | 326 | 4604.4298 | 69.0995 | 638.3144
[19 empty] | 327 | 4491.9505 | 66.8615 | 618.4235
[19 empty] | 328 | 4837.1864 | 73.4801 | 677.2664
[19 empty] | 329 | 4162.9393 | 59.525 | 1160.5297
[19 empty] | 330 | 5267.2851 | 80.9491 | 743.7279
[19 empty] | 331 | 4314.5464 | 63.1001 | 909.692
[19 empty] | 332 | 4867.7832 | 74.0354 | 682.2061
[19 empty] | 333 | 4449.3826 | 65.9882 | 610.664
[19 empty] | 334 | 4544.7125 | 67.923 | 627.857
[19 empty] | 335 | 5578.1723 | 85.9735 | 788.4676
[19 empty] | 336 | 4860.6232 | 73.9058 | 681.0535
[19 empty] | 337 | 4703.1743 | 70.9943 | 655.1602
[19 empty] | 338 | 5357.7398 | 82.4397 | 756.9982
[19 empty] | 339 | 4610.0552 | 69.2091 | 639.2884
[19 empty] | 340 | 4007.7263 | 55.3171 | 1111.2441
[19 empty] | 341 | 4660.2578 | 70.178 | 647.9023
[19 empty] | 342 | 5770.5814 | 88.9521 | 815.0018
[19 empty] | 343 | 4176.7012 | 59.8704 | 1164.125
[19 empty] | 344 | 5596.1484 | 86.2559 | 790.9824
[19 empty] | 345 | 4427.3384 | 65.5295 | 606.5882
[19 empty] | 346 | 5164.432 | 79.2232 | 728.3654
[19 empty] | 347 | 3933.9644 | 53.1431 | 1080.659
[19 empty] | 348 | 5587.6538 | 86.1226 | 789.795
[19 empty] | 349 | 4978.1093 | 76.0044 | 699.7224
[19 empty] | 350 | 5483.8482 | 84.4779 | 775.1471
[19 empty] | 351 | 4801.0702 | 72.819 | 671.3864
[19 empty] | 352 | 4671.5287 | 70.3934 | 649.8175
[19 empty] | 353 | 4070.4777 | 57.0681 | 1133.063
[19 empty] | 354 | 4202.5648 | 60.506 | 1170.5688
[19 empty] | 355 | 4333.6968 | 63.5235 | 913.5897
[19 empty] | 356 | 4835.695 | 73.4529 | 677.0246
[19 empty] | 357 | 5938.2584 | 91.4722 | 837.4581
[19 empty] | 358 | 5437.0967 | 83.7275 | 768.4652
[19 empty] | 359 | 4320.8543 | 63.2401 | 910.9854
[19 empty] | 360 | 5326.4116 | 81.9262 | 752.4267
[19 empty] | 361 | 5572.0459 | 85.8771 | 787.6089
[19 empty] | 362 | 4021.6295 | 55.7113 | 1116.3466
[19 empty] | 363 | 4219.4383 | 60.9121 | 888.8646
[19 empty] | 364 | 4096.0775 | 57.7642 | 1141.1834
[19 empty] | 365 | 3941.6181 | 53.3767 | 1084.1741
[19 empty] | 366 | 4478.3943 | 66.5851 | 615.9676
[19 empty] | 367 | 3996.5623 | 54.9975 | 1107.0183
[19 empty] | 368 | 5341.9161 | 82.1807 | 754.6924
[19 empty] | 369 | 5187.0764 | 79.6061 | 731.7736
[19 empty] | 370 | 5027.3114 | 76.8667 | 707.3949
[19 empty] | 371 | 4488.1128 | 66.7834 | 617.7296
[19 empty] | 372 | 5304.5588 | 81.5663 | 749.2226
[19 empty] | 373 | 4041.9182 | 56.2799 | 1123.5034
[19 empty] | 374 | 4509.5683 | 67.2184 | 621.5951
[19 empty] | 375 | 4202.3277 | 60.5002 | 1170.5115
[19 empty] | 376 | 5194.286 | 79.7277 | 732.8556
[19 empty] | 377 | 4720.5008 | 71.3209 | 658.0644
[19 empty] | 378 | 4155.9023 | 59.3462 | 1158.6421
[19 empty] | 379 | 5755.2872 | 88.7188 | 812.9231
[19 empty] | 380 | 4158.2166 | 59.4052 | 1159.2667
[19 empty] | 381 | 5473.5505 | 84.3131 | 773.68
[19 empty] | 382 | 4233.7735 | 61.2523 | 892.1837
[19 empty] | 383 | 5621.7687 | 86.6568 | 794.5536
[19 empty] | 384 | 5740.4964 | 88.4926 | 810.9078
[19 empty] | 385 | 4132.4167 | 58.7371 | 1152.0759
[19 empty] | 386 | 4015.7175 | 55.5442 | 1114.1977
[19 empty] | 387 | 4233.5183 | 61.2463 | 892.1253
[19 empty] | 388 | 4224.0693 | 61.0224 | 889.9448
[19 empty] | 389 | 4437.9951 | 65.7518 | 608.5636
[19 empty] | 390 | 5420.3287 | 83.4569 | 766.0555
[19 empty] | 391 | 5007.8096 | 76.5261 | 704.3636
[19 empty] | 392 | 4484.6423 | 66.7127 | 617.1012
[19 empty] | 393 | 5277.4722 | 81.1182 | 745.2333
[19 empty] | 394 | 4659.184 | 70.1574 | 647.7195
[19 empty] | 395 | 4923.3061 | 75.0327 | 691.0774
[19 empty] | 396 | 5329.0089 | 81.9689 | 752.8067
[19 empty] | 397 | 3975.4541 | 54.3851 | 1098.6794
[19 empty] | 398 | 4615.441 | 69.3138 | 640.2193
[19 empty] | 399 | 4641.3333 | 69.8146 | 644.6714
[19 empty] | 400 | 4967.0271 | 75.8089 | 697.9828
[19 empty] | 401 | 4340.3987 | 63.6705 | 914.9338
[19 empty] | 402 | 4050.6537 | 56.5224 | 1126.4879
[19 empty] | 403 | 3940.6722 | 53.348 | 1083.7449
[19 empty] | 404 | 4835.8015 | 73.4548 | 677.0419
[19 empty] | 405 | 4027.162 | 55.8672 | 1118.3309
[19 empty] | 406 | 4861.1117 | 73.9147 | 681.1322
[19 empty] | 407 | 3967.2581 | 54.1441 | 1095.3052
[19 empty] | 408 | 5474.9717 | 84.3359 | 773.8826
[19 empty] | 409 | 4521.6628 | 67.462 | 623.7595
[19 empty] | 410 | 4611.8619 | 69.2442 | 639.6009
[19 empty] | 411 | 5412.5892 | 83.3317 | 764.9409
[19 empty] | 412 | 3904.4594 | 52.2183 | 1066.0691
[19 empty] | 413 | 4659.4975 | 70.1634 | 647.7729
[19 empty] | 414 | 4302.2812 | 62.8262 | 907.1492
[19 empty] | 415 | 4516.5468 | 67.3591 | 622.8452
[19 empty] | 416 | 4187.9835 | 60.1497 | 1166.9837
[19 empty] | 417 | 5036.0707 | 77.0193 | 708.7523
[19 empty] | 418 | 4752.4598 | 71.9191 | 663.3839
[19 empty] | 419 | 4306.0573 | 62.9107 | 907.936
[19 empty] | 420 | 4105.4415 | 58.0165 | 1144.0583
[19 empty] | 421 | 4240.9645 | 61.4214 | 893.822
[19 empty] | 422 | 4736.3656 | 71.6186 | 660.7111
[19 empty] | 423 | 4885.2289 | 74.3502 | 685.0062
[19 empty] | 424 | 3986.9404 | 54.7198 | 1103.2767
[19 empty] | 425 | 5255.4569 | 80.7523 | 741.9763
[19 empty] | 426 | 5486.4145 | 84.5189 | 775.5124
[19 empty] | 427 | 4761.8899 | 72.0946 | 664.9445
[19 empty] | 428 | 4349.7362 | 63.8743 | 916.7899
[19 empty] | 429 | 4689.4188 | 70.7338 | 652.8441
[19 empty] | 430 | 4314.3898 | 63.0966 | 909.6598
[19 empty] | 431 | 5827.8238 | 89.8202 | 822.7365
[19 empty] | 432 | 3901.5707 | 52.1254 | 1064.5362
[19 empty] | 433 | 4272.4537 | 62.1507 | 900.8017
[19 empty] | 434 | 4259.8476 | 61.8609 | 898.0439
[19 empty] | 435 | 4466.4729 | 66.3408 | 613.7962
[19 empty] | 436 | 5278.369 | 81.1331 | 745.3657
[19 empty] | 437 | 5447.3238 | 83.8922 | 769.9315
[19 empty] | 438 | 4949.6257 | 75.5009 | 695.2426
[19 empty] | 439 | 4963.7857 | 75.7516 | 697.4732
[19 empty] | 440 | 5387.5538 | 82.9256 | 761.3251
[19 empty] | 441 | 4217.3049 | 60.8611 | 888.3643
[19 empty] | 442 | 4856.5124 | 73.8314 | 680.3908
[19 empty] | 443 | 5254.4388 | 80.7354 | 741.8254
[19 empty] | 444 | 5544.421 | 85.4411 | 783.7256
[19 empty] | 445 | 4646.8458 | 69.9207 | 645.6145
[19 empty] | 446 | 5784.0793 | 89.1576 | 816.8321
[19 empty] | 447 | 4260.09 | 61.8665 | 898.0974
[19 empty] | 448 | 5311.9932 | 81.6889 | 750.3141
[19 empty] | 449 | 4240.1975 | 61.4034 | 893.6481
[19 empty] | 450 | 5813.182 | 89.5989 | 820.7649
[19 empty] | 451 | 5093.7589 | 78.017 | 717.6302
[19 empty] | 452 | 4866.5571 | 74.0133 | 682.0089
[19 empty] | 453 | 5103.4135 | 78.1828 | 719.1057
[19 empty] | 454 | 4577.4236 | 68.5705 | 633.6124
[19 empty] | 455 | 4119.1224 | 58.3832 | 1148.1731
[19 empty] | 456 | 5436.0638 | 83.7109 | 768.317
[19 empty] | 457 | 5478.1983 | 84.3875 | 774.3425
[19 empty] | 458 | 4970.3931 | 75.8683 | 698.5116
[19 empty] | 459 | 5684.4661 | 87.6307 | 803.2295
[19 empty] | 460 | 5497.0888 | 84.6893 | 777.0298
[19 empty] | 461 | 4837.2938 | 73.482 | 677.2838
[19 empty] | 462 | 4500.6677 | 67.0384 | 619.9956
[19 empty] | 463 | 5628.5415 | 86.7625 | 795.4951
[19 empty] | 464 | 5411.0073 | 83.3061 | 764.7129
[19 empty] | 465 | 4571.1582 | 68.4471 | 632.5152
[19 empty] | 466 | 4522.3269 | 67.4753 | 623.8781
[19 empty] | 467 | 4846.7119 | 73.6534 | 678.8082
[19 empty] | 468 | 4331.2754 | 63.4702 | 913.1016
[19 empty] | 469 | 4469.0688 | 66.3941 | 614.27
[19 empty] | 470 | 4316.6695 | 63.1472 | 910.1284
[19 empty] | 471 | 4247.6001 | 61.5766 | 895.3185
[19 empty] | 472 | 5459.4722 | 84.0874 | 771.6699
[19 empty] | 473 | 5406.7906 | 83.2378 | 764.1048
[19 empty] | 474 | 5137.0235 | 78.7574 | 724.22
[19 empty] | 475 | 4918.5173 | 74.9472 | 690.3168
[19 empty] | 476 | 4129.4021 | 58.6573 | 1151.2009
[19 empty] | 477 | 4378.8996 | 64.5042 | 922.469
[19 empty] | 478 | 4676.8109 | 70.4941 | 650.7129
[19 empty] | 479 | 4805.0902 | 72.8929 | 672.0436
[19 empty] | 480 | 4081.8757 | 57.3792 | 1136.7275
[19 empty] | 481 | 3921.2599 | 52.7501 | 1074.5955
[19 empty] | 482 | 5240.4018 | 80.5012 | 739.7413
[19 empty] | 483 | 4320.4838 | 63.2319 | 910.9097
[19 empty] | 484 | 4091.1312 | 57.6304 | 1139.6449
[19 empty] | 485 | 3984.0925 | 54.6371 | 1102.1505
[19 empty] | 486 | 3960.0911 | 53.9318 | 1092.2856
[19 empty] | 487 | 4907.5523 | 74.7511 | 688.5721
[19 empty] | 488 | 4111.3578 | 58.1754 | 1145.8499
[19 empty] | 489 | 4594.5889 | 68.9073 | 636.6061
[19 empty] | 490 | 4360.1487 | 64.1004 | 918.8377
[19 empty] | 491 | 4335.2061 | 63.5566 | 913.8933
[19 empty] | 492 | 4105.9246 | 58.0295 | 1144.2053
[19 empty] | 493 | 4050.1571 | 56.5086 | 1126.3197
[19 empty] | 494 | 4516.493 | 67.358 | 622.8356
[19 empty] | 495 | 4101.6707 | 57.9151 | 1142.9065
[19 empty] | 496 | 4113.4837 | 58.2324 | 1146.4891
[19 empty] | 497 | 4351.663 | 63.9163 | 917.1706
[19 empty] | 498 | 3895.5016 | 51.9283 | 1061.2434
[19 empty] | 499 | 4150.5876 | 59.2102 | 1157.1931
[19 empty] | 500 | 4828.2698 | 73.3174 | 675.8197
[19 empty] | 501 | 4290.7422 | 62.5665 | 904.722
[19 empty] | 502 | 5073.486 | 77.6677 | 714.5224
[19 empty] | 503 | 5653.7765 | 87.1553 | 798.9939
[19 empty] | 504 | 4481.8272 | 66.6553 | 616.5908
[19 empty] | 505 | 5435.8278 | 83.7071 | 768.2831
[19 empty] | 506 | 5390.303 | 82.9703 | 761.7229
[19 empty] | 507 | 4801.207 | 72.8215 | 671.4087
[19 empty] | 508 | 5005.2403 | 76.4811 | 703.9633
[19 empty] | 509 | 4512.3488 | 67.2745 | 622.0936
[19 empty] | 510 | 4833.9689 | 73.4214 | 676.7447
[19 empty] | 511 | 4554.9193 | 68.1259 | 629.6601
[19 empty] | 512 | 5170.0493 | 79.3183 | 729.2122
[19 empty] | 513 | 4747.6088 | 71.8287 | 662.5796
[19 empty] | 514 | 5921.8074 | 91.228 | 835.2817
[19 empty] | 515 | 4675.6652 | 70.4723 | 650.5188
[19 empty] | 516 | 4212.1821 | 60.7382 | 887.156
[19 empty] | 517 | 5010.9877 | 76.5817 | 704.8585
[19 empty] | 518 | 5223.427 | 80.2173 | 737.2137
[19 empty] | 519 | 4505.3943 | 67.1341 | 620.8457
[19 empty] | 520 | 4189.4228 | 60.1851 | 1167.343
[19 empty] | 521 | 4096.5768 | 57.7777 | 1141.338
[19 empty] | 522 | 4053.9934 | 56.6148 | 1127.6144
[19 empty] | 523 | 4183.2077 | 60.0319 | 1165.783
[19 empty] | 524 | 4955.9517 | 75.613 | 696.24
[19 empty] | 525 | 4268.156 | 62.0522 | 899.8667
[19 empty] | 526 | 5145.8762 | 78.9081 | 725.5613
[19 empty] | 527 | 4067.8718 | 56.9967 | 1132.2136
[19 empty] | 528 | 4247.1035 | 61.565 | 895.207
[19 empty] | 529 | 4832.2078 | 73.3893 | 676.459
[19 empty] | 530 | 6025.0543 | 92.7498 | 848.8457
[19 empty] | 531 | 3998.1779 | 55.0439 | 1107.6373
[19 empty] | 532 | 4035.1982 | 56.0924 | 1121.1689
[19 empty] | 533 | 3956.4512 | 53.8233 | 1090.7261
[19 empty] | 534 | 4288.4727 | 62.5152 | 904.2405
[19 empty] | 535 | 4283.4148 | 62.4006 | 903.1623
[19 empty] | 536 | 4891.6893 | 74.4664 | 686.0401
[19 empty] | 537 | 4487.6919 | 66.7748 | 617.6534
[19 empty] | 538 | 4808.1613 | 72.9493 | 672.5452
[19 empty] | 539 | 4325.3686 | 63.3399 | 911.9052
[19 empty] | 540 | 3999.1145 | 55.0708 | 1107.995
[19 empty] | 541 | 5044.6758 | 77.1689 | 710.0834
[19 empty] | 542 | 5640.7746 | 86.9531 | 797.193
[19 empty] | 543 | 4875.1193 | 74.168 | 683.385
[19 empty] | 544 | 4649.7089 | 69.9757 | 646.1037
[19 empty] | 545 | 4587.3133 | 68.7648 | 635.3393
[19 empty] | 546 | 4491.8099 | 66.8586 | 618.3981
[19 empty] | 547 | 4674.9295 | 70.4583 | 650.3941
[19 empty] | 548 | 4527.4464 | 67.578 | 624.791
[19 empty] | 549 | 5683.5021 | 87.6158 | 803.0968
[19 empty] | 550 | 4793.368 | 72.6772 | 670.1253
[19 empty] | 551 | 5158.6882 | 79.1258 | 727.4985
[19 empty] | 552 | 4661.0823 | 70.1938 | 648.0426
[19 empty] | 553 | 5176.3924 | 79.4257 | 730.1674
[19 empty] | 554 | 5682.6057 | 87.602 | 802.9733
[19 empty] | 555 | 4775.8206 | 72.353 | 667.2427
[19 empty] | 556 | 4403.0776 | 65.0191 | 602.0537
[19 empty] | 557 | 4073.6233 | 57.1542 | 1134.0824
[19 empty] | 558 | 4263.5097 | 61.9453 | 898.8499
[19 empty] | 559 | 3927.2858 | 52.9374 | 1077.509
[19 empty] | 560 | 4401.4454 | 64.9845 | 601.7467
[19 empty] | 561 | 4785.8788 | 72.539 | 668.8966
[19 empty] | 562 | 4800.2675 | 72.8042 | 671.2551
[19 empty] | 563 | 4475.6025 | 66.528 | 615.46
[19 empty] | 564 | 6065.9881 | 93.3461 | 854.1609
[19 empty] | 565 | 4009.0744 | 55.3555 | 1111.7464
[19 empty] | 566 | 5244.8492 | 80.5755 | 740.4022
[19 empty] | 567 | 4418.1264 | 65.3364 | 604.8726
[19 empty] | 568 | 4986.5087 | 76.1523 | 701.038
[19 empty] | 569 | 4572.2335 | 68.4683 | 632.7037
[19 empty] | 570 | 4140.8994 | 58.9597 | 1154.4974
[19 empty] | 571 | 4592.695 | 68.8702 | 636.2766
[19 empty] | 572 | 5338.3347 | 82.122 | 754.1696
[19 empty] | 573 | 4484.2021 | 66.7037 | 617.0214
[19 empty] | 574 | 4848.9515 | 73.6941 | 679.1702
[19 empty] | 575 | 5138.381 | 78.7805 | 724.4258
[19 empty] | 576 | 4008.2104 | 55.3309 | 1111.4247
[19 empty] | 577 | 5088.9526 | 77.9343 | 716.8945
[19 empty] | 578 | 4604.333 | 69.0976 | 638.2977
[19 empty] | 579 | 4954.0015 | 75.5785 | 695.9327
[19 empty] | 580 | 4577.7673 | 68.5773 | 633.6725
[19 empty] | 581 | 4677.4577 | 70.5064 | 650.8224
[19 empty] | 582 | 4551.9256 | 68.0664 | 629.1319
[19 empty] | 583 | 4285.823 | 62.4552 | 903.6765
[19 empty] | 584 | 6134.0345 | 94.3284 | 862.9185
[19 empty] | 585 | 5865.9854 | 90.3944 | 827.8534
[19 empty] | 586 | 4605.629 | 69.1229 | 638.5222
[19 empty] | 587 | 5137.128 | 78.7592 | 724.2358
[19 empty] | 588 | 4406.2778 | 65.0868 | 602.6549
[19 empty] | 589 | 3884.9343 | 51.5791 | 1055.2517
[19 empty] | 590 | 3969.553 | 54.2118 | 1096.2582
[19 empty] | 591 | 4652.7731 | 70.0345 | 646.6268
[19 empty] | 592 | 5212.1811 | 80.0287 | 735.5347
[19 empty] | 593 | 4045.6234 | 56.3829 | 1124.7761
[19 empty] | 594 | 4879.2118 | 74.2418 | 684.0418
[19 empty] | 595 | 4324.0217 | 63.3102 | 911.6313
[19 empty] | 596 | 4758.6014 | 72.0335 | 664.4008
[19 empty] | 597 | 4581.5248 | 68.6512 | 634.3293
[19 empty] | 598 | 5227.1105 | 80.279 | 737.7629
[19 empty] | 599 | 4293.1635 | 62.6212 | 905.2342
[19 empty] | 600 | 4496.9347 | 66.9627 | 619.323
[19 empty] | 601 | 3924.718 | 52.8578 | 1076.276
[19 empty] | 602 | 4372.5911 | 64.3688 | 921.2552
[19 empty] | 603 | 4585.8583 | 68.7363 | 635.0856
[19 empty] | 604 | 4212.0032 | 60.7339 | 887.1136
[19 empty] | 605 | 4608.4794 | 69.1784 | 639.0158
[19 empty] | 606 | 4542.1917 | 67.8728 | 627.4106
[19 empty] | 607 | 5179.4158 | 79.4768 | 730.6223
[19 empty] | 608 | 4221.9039 | 60.9709 | 889.4407
[19 empty] | 609 | 4677.553 | 70.5082 | 650.8385
[19 empty] | 610 | 5234.7266 | 80.4064 | 738.8971
[19 empty] | 611 | 4337.2558 | 63.6016 | 914.3048
[19 empty] | 612 | 3960.2525 | 53.9366 | 1092.3544
[19 empty] | 613 | 4878.6127 | 74.231 | 683.9457
[19 empty] | 614 | 5184.7841 | 79.5674 | 731.4292
[19 empty] | 615 | 5508.7468 | 84.875 | 778.684
[19 empty] | 616 | 4198.9345 | 60.4178 | 1169.6873
[19 empty] | 617 | 4891.1883 | 74.4574 | 685.96
[19 empty] | 618 | 4189.1688 | 60.1789 | 1167.2797
[19 empty] | 619 | 4365.167 | 64.2089 | 919.8165
[19 empty] | 620 | 5958.189 | 91.7672 | 840.0872
[19 empty] | 621 | 4111.6113 | 58.1822 | 1145.9263
[19 empty] | 622 | 3996.0601 | 54.9831 | 1106.8254
[19 empty] | 623 | 4339.5467 | 63.6518 | 914.7635
[19 empty] | 624 | 4518.6778 | 67.402 | 623.2263
[19 empty] | 625 | 4209.9927 | 60.6855 | 1172.3506
[19 empty] | 626 | 5325.136 | 81.9052 | 752.24
[19 empty] | 627 | 5405.8335 | 83.2223 | 763.9668
[19 empty] | 628 | 4062.3412 | 56.8449 | 1130.3963
[19 empty] | 629 | 4078.5938 | 57.2898 | 1135.6806
[19 empty] | 630 | 4407.4436 | 65.1114 | 602.8737
[19 empty] | 631 | 4904.3777 | 74.6942 | 688.0662
[19 empty] | 632 | 4264.7138 | 61.9731 | 899.114
[19 empty] | 633 | 5542.6943 | 85.4138 | 783.4822
[19 empty] | 634 | 3910.7828 | 52.4202 | 1069.353
[19 empty] | 635 | 5229.6321 | 80.3212 | 738.1386
[19 empty] | 636 | 4925.0099 | 75.0631 | 691.3478
[19 empty] | 637 | 5149.1301 | 78.9635 | 726.0538
[19 empty] | 638 | 4671.8257 | 70.3991 | 649.8679
[19 empty] | 639 | 4662.7767 | 70.2262 | 648.3309
[19 empty] | 640 | 4727.7294 | 71.4567 | 659.2718
[19 empty] | 641 | 4336.418 | 63.5832 | 914.1367
[19 empty] | 642 | 4681.235 | 70.5783 | 651.4616
[19 empty] | 643 | 4440.1756 | 65.7972 | 608.9666
[19 empty] | 644 | 4666.5644 | 70.2986 | 648.9748
[19 empty] | 645 | 5078.2854 | 77.7505 | 715.2593
[19 empty] | 646 | 4833.8394 | 73.4191 | 676.7237
[19 empty] | 647 | 4447.07 | 65.9403 | 610.2383
[19 empty] | 648 | 5071.1785 | 77.6279 | 714.1678
[19 empty] | 649 | 4408.2471 | 65.1284 | 603.0244
[19 empty] | 650 | 4817.3351 | 73.1175 | 674.0411
[19 empty] | 651 | 4580.1454 | 68.6241 | 634.0883
[19 empty] | 652 | 4025.9194 | 55.8322 | 1117.8874
[19 empty] | 653 | 4058.8084 | 56.7476 | 1129.2248
[19 empty] | 654 | 5091.7708 | 77.9828 | 717.326
[19 empty] | 655 | 4881.499 | 74.283 | 684.4085
[19 empty] | 656 | 6033.9824 | 92.8802 | 850.008
[19 empty] | 657 | 5115.653 | 78.3925 | 720.9721
[19 empty] | 658 | 4321.9318 | 63.2639 | 911.2054
[19 empty] | 659 | 4809.0489 | 72.9655 | 672.6901
[19 empty] | 660 | 5178.9231 | 79.4684 | 730.5482
[19 empty] | 661 | 4590.0499 | 68.8184 | 635.8162
[19 empty] | 662 | 5957.5313 | 91.7574 | 840.0005
[19 empty] | 663 | 4386.7512 | 64.6721 | 923.9689
[19 empty] | 664 | 4131.7532 | 58.7196 | 1151.884
[19 empty] | 665 | 4292.0853 | 62.5968 | 905.0063
[19 empty] | 666 | 4057.1294 | 56.7014 | 1128.6651
[19 empty] | 667 | 4468.1286 | 66.3748 | 614.0985
[19 empty] | 668 | 3996.1984 | 54.9871 | 1106.8785
[19 empty] | 669 | 4334.573 | 63.5427 | 913.766
[19 empty] | 670 | 5273.0433 | 81.0447 | 744.5792
[19 empty] | 671 | 4816.3495 | 73.0994 | 673.8806
[19 empty] | 672 | 4037.5514 | 56.1582 | 1121.9903
[19 empty] | 673 | 5390.7599 | 82.9777 | 761.789
[19 empty] | 674 | 5037.1846 | 77.0387 | 708.9248
[19 empty] | 675 | 4977.6105 | 75.9956 | 699.6442
[19 empty] | 676 | 4559.5706 | 68.2181 | 630.4796
[19 empty] | 677 | 4387.1768 | 64.6812 | 924.0499
[19 empty] | 678 | 4374.6312 | 64.4127 | 921.6486
[19 empty] | 679 | 4303.5213 | 62.854 | 907.408
[19 empty] | 680 | 5633.1344 | 86.8341 | 796.133
[19 empty] | 681 | 4533.1305 | 67.6918 | 625.8025
[19 empty] | 682 | 5398.9544 | 83.1108 | 762.9736
[19 empty] | 683 | 4649.296 | 69.9678 | 646.0332
[19 empty] | 684 | 6116.8171 | 94.0809 | 860.7118
[19 empty] | 685 | 4805.1658 | 72.8942 | 672.0559
[19 empty] | 686 | 5236.6984 | 80.4394 | 739.1905
[19 empty] | 687 | 4996.672 | 76.3308 | 702.6267
[19 empty] | 688 | 4359.9134 | 64.0953 | 918.7917
[19 empty] | 689 | 4699.9042 | 70.9325 | 654.6105
[19 empty] | 690 | 4570.5258 | 68.4346 | 632.4044
[19 empty] | 691 | 4337.6816 | 63.6109 | 914.3901
[19 empty] | 692 | 5728.5345 | 88.3093 | 809.2745
[19 empty] | 693 | 4137.2133 | 58.8634 | 1153.4524
[19 empty] | 694 | 4222.7236 | 60.9904 | 889.6317
[19 empty] | 695 | 5860.2532 | 90.3084 | 827.0868
[19 empty] | 696 | 5410.9238 | 83.3048 | 764.7009
[19 empty] | 697 | 4903.4657 | 74.6779 | 687.9207
[19 empty] | 698 | 4802.7944 | 72.8507 | 671.6683
[19 empty] | 699 | 5359.5614 | 82.4694 | 757.2632
[19 empty] | 700 | 4058.4336 | 56.7373 | 1129.1
[19 empty] | 701 | 3922.9708 | 52.8034 | 1075.4299
[19 empty] | 702 | 4212.5388 | 60.7468 | 887.2404
[19 empty] | 703 | 5256.6853 | 80.7728 | 742.1584
[19 empty] | 704 | 4023.9344 | 55.7763 | 1117.1764
[19 empty] | 705 | 4497.8488 | 66.9813 | 619.4878
[19 empty] | 706 | 4619.3953 | 69.3905 | 640.9016
[19 empty] | 707 | 4823.6486 | 73.233 | 675.0687
[19 empty] | 708 | 5173.4392 | 79.3757 | 729.7228
[19 empty] | 709 | 5594.3546 | 86.2277 | 790.7318
[19 empty] | 710 | 4322.3812 | 63.2739 | 911.2971
[19 empty] | 711 | 4798.3542 | 72.769 | 670.942
[19 empty] | 712 | 4040.2952 | 56.2347 | 1122.9427
[19 empty] | 713 | 4232.281 | 61.2171 | 891.8415
[19 empty] | 714 | 4395.1245 | 64.8504 | 600.5555
[19 empty] | 715 | 4221.6328 | 60.9644 | 889.3774
[19 empty] | 716 | 5013.3057 | 76.6222 | 705.2192
[19 empty] | 717 | 4500.0878 | 67.0267 | 619.8912
[19 empty] | 718 | 4882.1644 | 74.295 | 684.5152
[19 empty] | 719 | 4628.1193 | 69.5595 | 642.404
[19 empty] | 720 | 5528.4917 | 85.1888 | 781.4781
[19 empty] | 721 | 4569.4515 | 68.4134 | 632.2159
[19 empty] | 722 | 5428.1762 | 83.5837 | 767.1842
[19 empty] | 723 | 4128.359 | 58.6295 | 1150.8963
[19 empty] | 724 | 4194.927 | 60.32 | 1168.7058
[19 empty] | 725 | 4091.4718 | 57.6396 | 1139.7513
[19 empty] | 726 | 4817.2142 | 73.1152 | 674.0215
[19 empty] | 727 | 3945.8779 | 53.5058 | 1086.0895
[19 empty] | 728 | 5227.9809 | 80.2936 | 737.8926
[19 empty] | 729 | 5496.7256 | 84.6835 | 776.9782
[19 empty] | 730 | 3897.8943 | 52.0063 | 1062.5536
[19 empty] | 731 | 4164.4282 | 59.5626 | 1160.9247
[19 empty] | 732 | 4391.2273 | 64.7675 | 924.8187
[19 empty] | 733 | 5126.0075 | 78.5695 | 722.5475
[19 empty] | 734 | 4597.6275 | 68.9667 | 637.1342
[19 empty] | 735 | 4212.4958 | 60.7458 | 887.2303
[19 empty] | 736 | 4186.0418 | 60.1019 | 1166.4972
[19 empty] | 737 | 3907.5129 | 52.3161 | 1067.6669
[19 empty] | 738 | 5757.6036 | 88.7542 | 813.2382
[19 empty] | 739 | 5374.4948 | 82.7131 | 759.4326
[19 empty] | 740 | 3985.5756 | 54.6802 | 1102.7381
[19 empty] | 741 | 4337.4263 | 63.6053 | 914.3389
[19 empty] | 742 | 5080.3567 | 77.7862 | 715.5771
[19 empty] | 743 | 4042.521 | 56.2967 | 1123.7112
[19 empty] | 744 | 4889.3269 | 74.424 | 685.6622
[19 empty] | 745 | 4541.1675 | 67.8523 | 627.2291
[19 empty] | 746 | 4971.9494 | 75.8958 | 698.756
[19 empty] | 747 | 4273.882 | 62.1834 | 901.1112
[19 empty] | 748 | 4445.3613 | 65.9049 | 609.9235
[19 empty] | 749 | 5653.8504 | 87.1564 | 799.0042
[19 empty] | 750 | 4492.7381 | 66.8775 | 618.5658
[19 empty] | 751 | 5546.3172 | 85.4711 | 783.9927
[19 empty] | 752 | 4161.113 | 59.4787 | 1160.0432
[19 empty] | 753 | 4944.0282 | 75.4016 | 694.3589
[19 empty] | 754 | 5765.9222 | 88.8811 | 814.3691
[19 empty] | 755 | 5145.2764 | 78.8979 | 725.4705
[19 empty] | 756 | 4298.8525 | 62.7492 | 906.4316
[19 empty] | 757 | 4236.0549 | 61.3061 | 892.7054
[19 empty] | 758 | 5021.2248 | 76.7606 | 706.4502
[19 empty] | 759 | 4732.1177 | 71.539 | 660.0036
[19 empty] | 760 | 4378.1148 | 64.4874 | 922.3184
[19 empty] | 761 | 4675.2652 | 70.4647 | 650.451
[19 empty] | 762 | 5310.5401 | 81.665 | 750.1008
[19 empty] | 763 | 4339.5401 | 63.6517 | 914.7622
[19 empty] | 764 | 4293.307 | 62.6244 | 905.2645
[19 empty] | 765 | 5056.4444 | 77.373 | 711.8999
[19 empty] | 766 | 4107.1899 | 58.0635 | 1144.5897
[19 empty] | 767 | 6064.9219 | 93.3306 | 854.0229
[19 empty] | 768 | 4920.8203 | 74.9883 | 690.6827
[19 empty] | 769 | 4892.5081 | 74.4812 | 686.171
[19 empty] | 770 | 5151.8158 | 79.0091 | 726.46
[19 empty] | 771 | 5122.2841 | 78.5059 | 721.9814
[19 empty] | 772 | 5889.1678 | 90.7415 | 830.9464
[19 empty] | 773 | 5222.5466 | 80.2025 | 737.0824
[19 empty] | 774 | 5265.719 | 80.9231 | 743.4962
[19 empty] | 775 | 4198.8601 | 60.4159 | 1169.6692
[19 empty] | 776 | 4819.9064 | 73.1645 | 674.4598
[19 empty] | 777 | 4495.5831 | 66.9353 | 619.0793
[19 empty] | 778 | 5093.3004 | 78.0091 | 717.56
[19 empty] | 779 | 4050.971 | 56.5312 | 1126.5953
[19 empty] | 780 | 4447.4831 | 65.9489 | 610.3144
[19 empty] | 781 | 5121.6837 | 78.4956 | 721.89
[19 empty] | 782 | 5475.1802 | 84.3392 | 773.9123
[19 empty] | 783 | 4606.414 | 69.1382 | 638.6582
[19 empty] | 784 | 4997.3356 | 76.3425 | 702.7303
[19 empty] | 785 | 4753.1798 | 71.9325 | 663.5032
[19 empty] | 786 | 4668.1761 | 70.3294 | 649.2485
[19 empty] | 787 | 4226.2136 | 61.0734 | 890.4424
[19 empty] | 788 | 4317.368 | 63.1628 | 910.2718
[19 empty] | 789 | 5937.9828 | 91.4681 | 837.4217
[19 empty] | 790 | 5087.7496 | 77.9136 | 716.7103
[19 empty] | 791 | 4551.6073 | 68.0601 | 629.0757
[19 empty] | 792 | 4179.5989 | 59.9424 | 1164.8666
[19 empty] | 793 | 4332.4381 | 63.4958 | 913.3362
[19 empty] | 794 | 4812.0149 | 73.02 | 673.174
[19 empty] | 795 | 3871.579 | 51.1247 | 1047.1202
[19 empty] | 796 | 4212.2148 | 60.739 | 887.1637
[19 empty] | 797 | 4260.0984 | 61.8666 | 898.0993
[19 empty] | 798 | 4562.385 | 68.2738 | 630.9748
[19 empty] | 799 | 4338.427 | 63.6273 | 914.5394
[19 empty] | 800 | 4546.1909 | 67.9524 | 628.1186
[19 empty] | 801 | 4438.202 | 65.7562 | 608.6019
[19 empty] | 802 | 4119.0796 | 58.3821 | 1148.1604
[19 empty] | 803 | 4234.0331 | 61.2584 | 892.2432
[19 empty] | 804 | 4231.4599 | 61.1977 | 891.653
[19 empty] | 805 | 5052.5074 | 77.3048 | 711.2927
[19 empty] | 806 | 4434.18 | 65.6724 | 607.8575
[19 empty] | 807 | 4148.2183 | 59.1493 | 1156.5405
[19 empty] | 808 | 4215.7746 | 60.8244 | 888.0044
[19 empty] | 809 | 4927.2637 | 75.1033 | 691.7053
[19 empty] | 810 | 4147.6177 | 59.1338 | 1156.3744
[19 empty] | 811 | 5924.8861 | 91.2737 | 835.6894
[19 empty] | 812 | 4550.2694 | 68.0335 | 628.8395
[19 empty] | 813 | 4192.6481 | 60.2642 | 1168.1436
[19 empty] | 814 | 5633.1102 | 86.8337 | 796.1296
[19 empty] | 815 | 5466.3916 | 84.1984 | 772.6585
[19 empty] | 816 | 4431.3326 | 65.613 | 607.3298
[19 empty] | 817 | 5104.9665 | 78.2094 | 719.3428
[19 empty] | 818 | 4408.0117 | 65.1234 | 602.9802
[19 empty] | 819 | 4141.3976 | 58.9727 | 1154.6377
[19 empty] | 820 | 5567.979 | 85.8131 | 787.0383
[19 empty] | 821 | 4436.3267 | 65.7171 | 608.255
[19 empty] | 822 | 4085.3261 | 57.473 | 1137.821
[19 empty] | 823 | 5479.209 | 84.4037 | 774.4865
[19 empty] | 824 | 4555.8741 | 68.1448 | 629.8285
[19 empty] | 825 | 4445.1306 | 65.9001 | 609.881
[19 empty] | 826 | 4378.338 | 64.4922 | 922.3613
[19 empty] | 827 | 5050.3257 | 77.2669 | 710.956
[19 empty] | 828 | 5514.4805 | 84.9662 | 779.4963
[19 empty] | 829 | 4091.809 | 57.6488 | 1139.8566
[19 empty] | 830 | 4851.6949 | 73.7439 | 679.6134
[19 empty] | 831 | 5260.9816 | 80.8443 | 742.7949
[19 empty] | 832 | 4012.5406 | 55.4541 | 1113.0304
[19 empty] | 833 | 4729.1086 | 71.4826 | 659.5019
[19 empty] | 834 | 4139.3285 | 58.9187 | 1154.0534
[19 empty] | 835 | 4070.3489 | 57.0646 | 1133.0211
[19 empty] | 836 | 5024.7472 | 76.822 | 706.9971
[19 empty] | 837 | 4809.0198 | 72.965 | 672.6853
[19 empty] | 838 | 4083.3031 | 57.418 | 1137.1807
[19 empty] | 839 | 5209.1177 | 79.9772 | 735.0767
[19 empty] | 840 | 4674.752 | 70.4549 | 650.364
[19 empty] | 841 | 4798.2945 | 72.7679 | 670.9322
[19 empty] | 842 | 4698.2859 | 70.9019 | 654.3382
[19 empty] | 843 | 4286.5258 | 62.4711 | 903.8263
[19 empty] | 844 | 4251.618 | 61.6701 | 896.2178
[19 empty] | 845 | 4435.1167 | 65.6919 | 608.031
[19 empty] | 846 | 5783.1097 | 89.1428 | 816.7008
[19 empty] | 847 | 4707.9309 | 71.0841 | 655.959
[19 empty] | 848 | 5023.3604 | 76.7978 | 706.7818
[19 empty] | 849 | 3993.4036 | 54.9066 | 1105.8005
[19 empty] | 850 | 4580.0736 | 68.6226 | 634.0757
[19 empty] | 851 | 5904.2375 | 90.9664 | 832.9509
[19 empty] | 852 | 5367.6358 | 82.6013 | 758.4369
[19 empty] | 853 | 5384.2074 | 82.8712 | 760.8405
[19 empty] | 854 | 4963.6223 | 75.7487 | 697.4475
[19 empty] | 855 | 4227.0454 | 61.0931 | 890.635
[19 empty] | 856 | 4984.2159 | 76.112 | 700.6791
[19 empty] | 857 | 4490.9202 | 66.8406 | 618.2373
[19 empty] | 858 | 5930.2664 | 91.3536 | 836.4015
[19 empty] | 859 | 4491.7277 | 66.857 | 618.3832
[19 empty] | 860 | 4948.4054 | 75.4792 | 695.05
[19 empty] | 861 | 4877.421 | 74.2095 | 683.7545
[19 empty] | 862 | 4007.5492 | 55.3121 | 1111.178
[19 empty] | 863 | 4305.0669 | 62.8886 | 907.73
[19 empty] | 864 | 5174.2919 | 79.3901 | 729.8512
[19 empty] | 865 | 5003.8497 | 76.4567 | 703.7465
[19 empty] | 866 | 4378.4864 | 64.4954 | 922.3897
[19 empty] | 867 | 4205.8923 | 60.5866 | 1171.3706
[19 empty] | 868 | 4630.6761 | 69.609 | 642.8435
[19 empty] | 869 | 4276.4638 | 62.2423 | 901.6692
[19 empty] | 870 | 5123.1521 | 78.5207 | 722.1134
[19 empty] | 871 | 4308.9747 | 62.9759 | 908.5415
[19 empty] | 872 | 5008.2751 | 76.5342 | 704.4361
[19 empty] | 873 | 4411.2752 | 65.1922 | 603.5918
[19 empty] | 874 | 5511.3924 | 84.9171 | 779.0589
[19 empty] | 875 | 4078.119 | 57.2769 | 1135.5286
[19 empty] | 876 | 4588.1831 | 68.7819 | 635.4909
[19 empty] | 877 | 4661.8198 | 70.2079 | 648.1681
[19 empty] | 878 | 4139.3849 | 58.9202 | 1154.0693
[19 empty] | 879 | 4081.3616 | 57.3652 | 1136.5639
[19 empty] | 880 | 4251.9144 | 61.677 | 896.2839
[19 empty] | 881 | 4930.2264 | 75.1561 | 692.175
[19 empty] | 882 | 4820.8429 | 73.1817 | 674.6122
[19 empty] | 883 | 5925.9813 | 91.29 | 835.8344
[19 empty] | 884 | 4875.7157 | 74.1787 | 683.4808
[19 empty] | 885 | 5089.3761 | 77.9416 | 716.9594
[19 empty] | 886 | 4132.0456 | 58.7273 | 1151.9686
[19 empty] | 887 | 3907.1641 | 52.305 | 1067.4855
[19 empty] | 888 | 4601.0979 | 69.0345 | 637.7367
[19 empty] | 889 | 5192.7139 | 79.7012 | 732.6197
[19 empty] | 890 | 4467.5327 | 66.3625 | 613.9897
[19 empty] | 891 | 4053.26 | 56.5945 | 1127.3677
[19 empty] | 892 | 4397.3846 | 64.8984 | 600.9819
[19 empty] | 893 | 4603.4697 | 69.0808 | 638.148
[19 empty] | 894 | 3894.8196 | 51.906 | 1060.8669
[19 empty] | 895 | 4231.3733 | 61.1956 | 891.633
[19 empty] | 896 | 4760.947 | 72.0771 | 664.7887
[19 empty] | 897 | 4723.5178 | 71.3776 | 658.5687
[19 empty] | 898 | 5076.5851 | 77.7212 | 714.9983
[19 empty] | 899 | 4973.2403 | 75.9186 | 698.9587
[19 empty] | 900 | 5275.937 | 81.0927 | 745.0066
[19 empty] | 901 | 4668.4266 | 70.3342 | 649.2911
[19 empty] | 902 | 4143.9513 | 59.039 | 1155.3544
[19 empty] | 903 | 4677.5517 | 70.5082 | 650.8383
[19 empty] | 904 | 4029.7636 | 55.9402 | 1119.2553
[19 empty] | 905 | 4032.3989 | 56.0141 | 1120.1861
[19 empty] | 906 | 4519.2123 | 67.4127 | 623.3218
[19 empty] | 907 | 4701.0417 | 70.954 | 654.8018
[19 empty] | 908 | 4197.1728 | 60.3748 | 1169.2569
[19 empty] | 909 | 4418.4815 | 65.3439 | 604.9389
[19 empty] | 910 | 5892.0762 | 90.785 | 831.3337
[19 empty] | 911 | 4041.7056 | 56.274 | 1123.4301
[19 empty] | 912 | 4553.1324 | 68.0904 | 629.3449
[19 empty] | 913 | 4405.8073 | 65.0768 | 602.5666
[19 empty] | 914 | 4582.9458 | 68.6791 | 634.5774
[19 empty] | 915 | 4096.7984 | 57.7836 | 1141.4065
[19 empty] | 916 | 4857.1569 | 73.843 | 680.4948
[19 empty] | 917 | 4224.1033 | 61.0233 | 889.9527
[19 empty] | 918 | 5538.2746 | 85.3438 | 782.8591
[19 empty] | 919 | 4023.3222 | 55.7591 | 1116.9564
[19 empty] | 920 | 3918.2237 | 52.655 | 1073.1002
[19 empty] | 921 | 4119.871 | 58.4032 | 1148.3954
[19 empty] | 922 | 4557.4175 | 68.1754 | 630.1004
[19 empty] | 923 | 4006.1162 | 55.2712 | 1110.642
[19 empty] | 924 | 5083.4704 | 77.8399 | 716.0546
[19 empty] | 925 | 5192.0511 | 79.69 | 732.5203
[19 empty] | 926 | 4030.5465 | 55.9622 | 1119.5324
[19 empty] | 927 | 4539.7444 | 67.824 | 626.9768
[19 empty] | 928 | 3917.6668 | 52.6376 | 1072.8239
[19 empty] | 929 | 4872.7642 | 74.1254 | 683.0068
[19 empty] | 930 | 4844.4323 | 73.612 | 678.4396
[19 empty] | 931 | 4206.6646 | 60.6052 | 1171.5559
[19 empty] | 932 | 4819.2094 | 73.1518 | 674.3464
[19 empty] | 933 | 3999.6906 | 55.0874 | 1108.2146
[19 empty] | 934 | 4912.3539 | 74.837 | 689.3367
[19 empty] | 935 | 4619.5643 | 69.3938 | 640.9308
[19 empty] | 936 | 4393.4679 | 64.8152 | 925.2426
[19 empty] | 937 | 5797.0939 | 89.3552 | 818.5931
[19 empty] | 938 | 4359.4059 | 64.0843 | 918.6924
[19 empty] | 939 | 3924.1097 | 52.8389 | 1075.9821
[19 empty] | 940 | 4371.5293 | 64.346 | 921.0501
[19 empty] | 941 | 4871.7345 | 74.1068 | 682.8414
[19 empty] | 942 | 4128.2569 | 58.6268 | 1150.8665
[19 empty] | 943 | 5409.6985 | 83.2849 | 764.5242
[19 empty] | 944 | 3989.027 | 54.7802 | 1104.0963
[19 empty] | 945 | 4991.5849 | 76.2415 | 701.832
[19 empty] | 946 | 4713.0025 | 71.1798 | 656.8094
[19 empty] | 947 | 4521.3807 | 67.4563 | 623.7092
[19 empty] | 948 | 4836.7472 | 73.4721 | 677.1952
[19 empty] | 949 | 4403.4617 | 65.0272 | 602.1259
[19 empty] | 950 | 5994.1798 | 92.2974 | 844.8133
[19 empty] | 951 | 5915.1628 | 91.1291 | 834.401
[19 empty] | 952 | 3935.434 | 53.1882 | 1081.3415
[19 empty] | 953 | 5118.0416 | 78.4333 | 721.3358
[19 empty] | 954 | 4566.6071 | 68.3572 | 631.7167
[19 empty] | 955 | 4611.9152 | 69.2452 | 639.6101
[19 empty] | 956 | 4337.186 | 63.6001 | 914.2908
[19 empty] | 957 | 5060.6815 | 77.4464 | 712.5528
[19 empty] | 958 | 4953.119 | 75.5628 | 695.7935
[19 empty] | 959 | 5823.094 | 89.7488 | 822.1001
[19 empty] | 960 | 4970.1019 | 75.8632 | 698.4659
[19 empty] | 961 | 5372.0529 | 82.6733 | 759.0783
[19 empty] | 962 | 4378.5755 | 64.4973 | 922.4068
[19 empty] | 963 | 6002.3415 | 92.4172 | 845.8812
[19 empty] | 964 | 4998.7555 | 76.3674 | 702.9519
[19 empty] | 965 | 4812.4322 | 73.0276 | 673.2421
[19 empty] | 966 | 4957.3271 | 75.6374 | 696.4567
[19 empty] | 967 | 5872.6495 | 90.4943 | 828.7437
[19 empty] | 968 | 4976.4657 | 75.9755 | 699.4647
[19 empty] | 969 | 4366.5885 | 64.2396 | 920.0928
[19 empty] | 970 | 3896.6813 | 51.9668 | 1061.8914
[19 empty] | 971 | 4214.5398 | 60.7948 | 887.7133
[19 empty] | 972 | 5627.5658 | 86.7473 | 795.3595
[19 empty] | 973 | 5585.6849 | 86.0916 | 789.5195
[19 empty] | 974 | 4363.5681 | 64.1744 | 919.5052
[19 empty] | 975 | 4429.6055 | 65.5769 | 607.0093
[19 empty] | 976 | 4229.1095 | 61.1421 | 891.1118
[19 empty] | 977 | 4666.1168 | 70.2901 | 648.8987
[19 empty] | 978 | 5125.6633 | 78.5636 | 722.4952
[19 empty] | 979 | 4887.3004 | 74.3875 | 685.3379
[19 empty] | 980 | 4046.235 | 56.3999 | 1124.9852
[19 empty] | 981 | 4913.1076 | 74.8505 | 689.4566
[19 empty] | 982 | 4725.2813 | 71.4107 | 658.8632
[19 empty] | 983 | 5208.9427 | 79.9743 | 735.0505
[19 empty] | 984 | 5187.9973 | 79.6216 | 731.9119
[19 empty] | 985 | 5056.3382 | 77.3712 | 711.8835
[19 empty] | 986 | 4149.8177 | 59.1904 | 1156.9815
[19 empty] | 987 | 4881.2925 | 74.2793 | 684.3754
[19 empty] | 988 | 4272.453 | 62.1507 | 900.8015
[19 empty] | 989 | 4384.1859 | 64.6174 | 923.4802
[19 empty] | 990 | 4906.5283 | 74.7327 | 688.4089
[19 empty] | 991 | 3981.9658 | 54.5752 | 1101.3037
[19 empty] | 992 | 4424.0782 | 65.4613 | 605.9819
[19 empty] | 993 | 4596.0519 | 68.9359 | 636.8604
[19 empty] | 994 | 4714.8002 | 71.2136 | 657.1105
[19 empty] | 995 | 4362.1071 | 64.1428 | 919.2203
[19 empty] | 996 | 5283.8895 | 81.2246 | 746.1803
[19 empty] | 997 | 5414.7765 | 83.3671 | 765.2561
[19 empty] | 998 | 4950.7165 | 75.5202 | 695.4147
[19 empty] | 999 | 4401.8927 | 64.994 | 601.8309
[19 empty] | 1000 | 4707.586 | 71.0776 | 655.9011
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Cost Time Optimization 02
Activity | Immediate Predecessors | Immediate Followers | Pessimistic |  |  | Optimistic |  |  | Random Time & Cost
|  |  | Cost | Time | Cost / Time | Cost | Time | Cost / Time | Cost | Time | Cost / Time
A | - | C | 350 | 4 | 87.5 | 550 | 10 | 55 | 350.6543 | 15.2312 | 73.9795
B | - | C | 100 | 2 | 50 | 150 | 7 | 21.4286 | 173.5302 | 9.3285 | 5.9577 | Iiteration | Cost | Time | Cost/Time | MIN | 4469.9891
C | A,B | D,E,G | 256 | 4 | 64 | 400 | 8 | 50 | 424.868 | 8.8988 | 58.926 | 1 | 5528.5333 | 85.0171 | 753.422 | Q 25 - 1.5 L | 4099.7554
D | C | H | 52 | 15 | 3.4667 | 105 | 21 | 5 | 137.8749 | 15.5342 | 4.0424 | 2 | 5920.5746 | 107.5676 | 670.537 | Q 25 | 5632.4636
E | C | F | 31 | 6 | 5.1667 | 63 | 10 | 6.3 | 82.4733 | 11.8554 | 6.5315 | 3 | 5242.1116 | 106.5352 | 807.3491 | Q 50 | 6170.0811
F | E | H,I | 20 | 6 | 3.3333 | 45 | 8 | 5.625 | 37.6647 | 9.0183 | 3.8041 | 4 | 5366.7069 | 92.6 | 653.5005 | Q 75 | 6654.269
G | C | H,I | 45 | 7 | 6.4286 | 92 | 12 | 7.6667 | 103.0651 | 13.8371 | 7.4561 | 5 | 7498.1146 | 107.1654 | 950.3991 | Q 75 + 1.5 L | 8186.9771
H | D,F,G | J | 20 | 4 | 5 | 40 | 10 | 4 | 32.4459 | 7.6886 | 3.2486 | 6 | 6277.7792 | 103.6244 | 691.2802 | MAX | 7958.6912
I | G,F | K | 39 | 7 | 5.5714 | 85 | 10 | 8.5 | 104.8167 | 9.9165 | 11.0341 | 7 | 5802.5965 | 75.16 | 741.5983 | MEAN | 6161.7471
J | H | K | 10 | 4 | 2.5 | 21 | 6 | 3.5 | 31.5061 | 4.6721 | 4.1373 | 8 | 6528.5331 | 115.3572 | 843.1384 | STD | 705.2326
K | I,J | - | 25 | 20 | 1.25 | 30 | 40 | 0.75 | 30.2208 | 27.6526 | 1.0602 | 9 | 6375.8591 | 115.1021 | 527.3979 | P >=MEDIAN | 100%
Total: |  |  | 948 | 79 | 234.2167 | 1581 | 142 | 167.7702 | 1509.12 | 133.6335 | 180.1776 | 10 | 4692.6872 | 114.6024 | 728.5526
[12 empty] | 11 | 6572.5618 | 84.2674 | 644.4563
| Cost |  | Time |  | Cost / Time | [6 empty] | 12 | 5855.8768 | 98.6868 | 624.7259
Activity | ES | EF | ES | EF | ES | EF | [5 empty] | 13 | 5868.4611 | 98.1407 | 536.0522
A | 0 | 350.6543 | 0 | 15.2312 | 0 | 73.9795 | [5 empty] | 14 | 5085.999 | 91.7245 | 536.1485
B | 0 | 173.5302 | 0 | 9.3285 | 0 | 5.9577 | [5 empty] | 15 | 5982.2275 | 102.7264 | 817.7631 | MIN | 65.3249
C | 524.1845 | 949.0525 | 15.2312 | 24.1301 | 79.9372 | 138.8632 | [5 empty] | 16 | 6930.8162 | 88.582 | 535.7303 | Q 25 - 1.5 L | 57.5147
D | 949.0525 | 1086.9274 | 24.1301 | 39.6643 | 138.8632 | 142.9056 | [5 empty] | 17 | 6834.6501 | 102.7355 | 799.8402 | Q 25 | 86.946
E | 949.0525 | 1031.5258 | 24.1301 | 35.9855 | 138.8632 | 145.3946 | [5 empty] | 18 | 6430.4198 | 77.8881 | 675.3053 | Q 50 | 97.2279
F | 1031.5258 | 1069.1906 | 35.9855 | 45.0038 | 145.3946 | 149.1988 | [5 empty] | 19 | 6529.638 | 105.555 | 631.0449 | Q 75 | 106.5669
G | 949.0525 | 1052.1177 | 24.1301 | 37.9672 | 138.8632 | 146.3193 | [5 empty] | 20 | 7293.0239 | 84.4426 | 567.969 | Q 75 + 1.5 L | 135.9981
H | 3208.2356 | 3240.6816 | 45.0038 | 52.6924 | 438.4236 | 441.6722 | [5 empty] | 21 | 5376.1024 | 80.5294 | 572.3861 | MAX | 126.7634
I | 2121.3082 | 2226.1249 | 45.0038 | 54.9203 | 295.5181 | 306.5522 | [5 empty] | 22 | 7510.5107 | 93.7289 | 508.696 | MEAN | 96.7071
J | 3240.6816 | 3272.1876 | 52.6924 | 57.3645 | 441.6722 | 445.8096 | [5 empty] | 23 | 6944.0753 | 82.7323 | 962.552 | STD | 12.612
K | 5498.3125 | 5528.5333 | 57.3645 | 85.0171 | 752.3617 | 753.422 | [5 empty] | 24 | 5618.9335 | 112.9816 | 763.6364 | P >=MEDIAN | 100%
[12 empty] | 25 | 5838.2608 | 108.0036 | 1005.0157
[12 empty] | 26 | 6398.4966 | 116.2158 | 950.5299
| Target Cost: |  | 5528.5333 | [8 empty] | 27 | 6419.0515 | 91.5998 | 862.7927
| Target Time: |  | 85.0171 | [8 empty] | 28 | 5589.7356 | 78.385 | 540.4979
| Target Cost/Time: |  | 753.422 | [8 empty] | 29 | 5494.1846 | 71.6876 | 634.8361
[12 empty] | 30 | 5606.1084 | 99.5139 | 470.9149 | MIN | 344.4173
[12 empty] | 31 | 6797.0421 | 111.2614 | 482.7498 | Q 25 - 1.5 L | 331.843
[12 empty] | 32 | 6141.3322 | 93.626 | 620.9376 | Q 25 | 608.9623
[12 empty] | 33 | 6982.5608 | 94.3675 | 617.3697 | Q 50 | 696.36
[12 empty] | 34 | 7020.4755 | 97.9259 | 1005.2032 | Q 75 | 793.7086
[12 empty] | 35 | 7127.2315 | 89.9912 | 911.3046 | Q 75 + 1.5 L | 1070.8279
[12 empty] | 36 | 7144.5466 | 107.7309 | 413.7135 | MAX | 1043.1648
[12 empty] | 37 | 6437.7533 | 82.0877 | 759.6949 | MEAN | 698.7095
[12 empty] | 38 | 5784.9243 | 81.7019 | 661.2972 | STD | 130.3149
[12 empty] | 39 | 5627.056 | 74.0323 | 476.5635 | P >=MEDIAN | 0%
[12 empty] | 40 | 5806.4748 | 97.8857 | 653.0215
[12 empty] | 41 | 5242.3721 | 91.0866 | 717.5409
[12 empty] | 42 | 6787.9987 | 100.1095 | 778.8874
[12 empty] | 43 | 6571.1157 | 114.5025 | 622.4937
[12 empty] | 44 | 5055.017 | 114.6159 | 585.3535
[12 empty] | 45 | 6829.8224 | 82.3338 | 592.201
[12 empty] | 46 | 5258.4795 | 109.0622 | 774.546
[12 empty] | 47 | 6623.9391 | 108.4285 | 438.375
[12 empty] | 48 | 6885.53 | 71.2653 | 725.0417
[12 empty] | 49 | 6824.9005 | 115.3571 | 708.9096
[12 empty] | 50 | 6098.04 | 84.5635 | 890.9968
[12 empty] | 51 | 6019.4911 | 81.8714 | 759.7924
[12 empty] | 52 | 6542.8468 | 92.585 | 944.2956
[12 empty] | 53 | 6742.898 | 101.0768 | 822.3315
[12 empty] | 54 | 5694.8872 | 90.0827 | 512.0841
[12 empty] | 55 | 6608.6289 | 74.8884 | 851.5483
[12 empty] | 56 | 5908.3608 | 119.5463 | 670.6053
[12 empty] | 57 | 5395.6043 | 94.16 | 673.1092
[12 empty] | 58 | 6951.5063 | 85.2878 | 899.2809
[12 empty] | 59 | 5518.025 | 93.4155 | 861.233
[12 empty] | 60 | 6675.409 | 108.973 | 534.0921
[12 empty] | 61 | 6602.3149 | 97.4051 | 869.9877
[12 empty] | 62 | 5867.3073 | 100.4544 | 971.0362
[12 empty] | 63 | 5039.387 | 102.7481 | 715.0568
[12 empty] | 64 | 6423.3932 | 106.2017 | 724.9404
[12 empty] | 65 | 6566.3288 | 96.2679 | 840.8334
[12 empty] | 66 | 5633.4138 | 108.7616 | 629.3581
[12 empty] | 67 | 5772.9939 | 77.953 | 930.5475
[12 empty] | 68 | 6950.5887 | 81.5214 | 469.6372
[12 empty] | 69 | 5808.7573 | 116.122 | 657.8237
[12 empty] | 70 | 6986.1604 | 103.0392 | 684.8928
[12 empty] | 71 | 6220.9704 | 107.2565 | 528.1052
[12 empty] | 72 | 6222.4205 | 92.2425 | 572.7011
[12 empty] | 73 | 5327.8323 | 76.03 | 954.6891
[12 empty] | 74 | 6409.6511 | 85.3058 | 786.027
[12 empty] | 75 | 5971.4042 | 119.1755 | 733.7862
[12 empty] | 76 | 6081.2107 | 94.8002 | 667.9384
[12 empty] | 77 | 5600.32 | 109.214 | 400.1109
[12 empty] | 78 | 5097.222 | 85.2481 | 579.5088
[12 empty] | 79 | 5528.4185 | 78.9644 | 624.1447
[12 empty] | 80 | 6509.5552 | 93.1469 | 567.6791
[12 empty] | 81 | 5207.0994 | 98.3281 | 465.2293
[12 empty] | 82 | 5887.7 | 94.7371 | 621.1851
[12 empty] | 83 | 6919.613 | 102.7518 | 521.9487
[12 empty] | 84 | 7205.2813 | 83.789 | 724.7471
[12 empty] | 85 | 7008.7443 | 89.1565 | 863.8143
[12 empty] | 86 | 6807.3683 | 83.776 | 540.073
[12 empty] | 87 | 7739.3069 | 109.7022 | 528.4586
[12 empty] | 88 | 5720.9225 | 86.9331 | 781.8774
[12 empty] | 89 | 5292.9749 | 103.5142 | 736.236
[12 empty] | 90 | 7686.5737 | 77.6009 | 698.5239
[12 empty] | 91 | 5122.6161 | 74.7189 | 689.0825
[12 empty] | 92 | 6225.3041 | 99.4532 | 887.9925
[12 empty] | 93 | 7639.5548 | 80.7848 | 842.5733
[12 empty] | 94 | 5936.3514 | 99.3255 | 838.5425
[12 empty] | 95 | 5412.3063 | 83.1019 | 724.7183
[12 empty] | 96 | 6931.086 | 103.2303 | 713.6253
[12 empty] | 97 | 5434.4162 | 85.3804 | 865.861
[12 empty] | 98 | 6189.6772 | 94.082 | 696.6256
[12 empty] | 99 | 6247.7806 | 110.6431 | 626.2389
[12 empty] | 100 | 5560.018 | 105.5501 | 829.6951
[12 empty] | 101 | 7104.942 | 81.2149 | 344.4173
[12 empty] | 102 | 5706.0403 | 109.4221 | 617.3301
[12 empty] | 103 | 5390.5281 | 100.5465 | 606.3
[12 empty] | 104 | 6787.6199 | 86.4368 | 695.5064
[12 empty] | 105 | 6099.9934 | 100.3065 | 562.3429
[12 empty] | 106 | 7401.9003 | 87.4285 | 691.7319
[12 empty] | 107 | 7082.3805 | 107.1033 | 730.9956
[12 empty] | 108 | 5446.9477 | 99.9047 | 720.4449
[12 empty] | 109 | 5898.8921 | 91.4242 | 665.0199
[12 empty] | 110 | 5997.5429 | 112.5158 | 584.3054
[12 empty] | 111 | 6947.3492 | 67.2838 | 759.3709
[12 empty] | 112 | 6258.562 | 105.0165 | 831.5543
[12 empty] | 113 | 5206.33 | 113.3465 | 588.0154
[12 empty] | 114 | 5216.8248 | 92.1439 | 691.5084
[12 empty] | 115 | 6136.4531 | 106.9135 | 623.9143
[12 empty] | 116 | 5341.2885 | 88.8097 | 849.618
[12 empty] | 117 | 5415.7634 | 97.5981 | 496.1443
[12 empty] | 118 | 6854.5177 | 72.4603 | 820.628
[12 empty] | 119 | 5466.172 | 93.4637 | 717.0038
[12 empty] | 120 | 6491.0788 | 104.1496 | 757.9027
[12 empty] | 121 | 6538.4774 | 109.0942 | 534.1199
[12 empty] | 122 | 7776.3454 | 91.6912 | 804.2777
[12 empty] | 123 | 6453.7416 | 106.4179 | 890.5429
[12 empty] | 124 | 6520.4963 | 94.569 | 760.6045
[12 empty] | 125 | 6176.9118 | 92.6041 | 869.5284
[12 empty] | 126 | 6348.6353 | 99.4758 | 728.9842
[12 empty] | 127 | 5988.2315 | 97.7055 | 782.4015
[12 empty] | 128 | 5829.2816 | 88.5902 | 461.0138
[12 empty] | 129 | 6043.2229 | 117.2596 | 742.6235
[12 empty] | 130 | 5899.9568 | 101.9974 | 809.1296
[12 empty] | 131 | 6348.2322 | 79.2405 | 888.7342
[12 empty] | 132 | 6838.0046 | 110.2292 | 495.0971
[12 empty] | 133 | 6480.9889 | 80.3416 | 744.8843
[12 empty] | 134 | 6573.3797 | 81.795 | 547.4564
[12 empty] | 135 | 6392.062 | 85.2458 | 685.4961
[12 empty] | 136 | 6772.2061 | 121.1969 | 666.0334
[12 empty] | 137 | 6225.6874 | 89.3168 | 805.8685
[12 empty] | 138 | 5574.7188 | 74.8661 | 680.5239
[12 empty] | 139 | 6241.1255 | 88.0833 | 613.4148
[12 empty] | 140 | 6644.477 | 91.2974 | 701.6127
[12 empty] | 141 | 5665.1617 | 91.6691 | 856.284
[12 empty] | 142 | 6652.0341 | 103.2246 | 832.3814
[12 empty] | 143 | 5419.6765 | 109.8735 | 592.9639
[12 empty] | 144 | 5729.399 | 88.4344 | 614.9325
[12 empty] | 145 | 5775.7003 | 91.8558 | 667.0324
[12 empty] | 146 | 5996.6936 | 86.8977 | 463.1033
[12 empty] | 147 | 5112.267 | 115.3687 | 819.7683
[12 empty] | 148 | 5645.886 | 111.577 | 785.0647
[12 empty] | 149 | 6599.2029 | 88.1433 | 539.9554
[12 empty] | 150 | 6340.4032 | 103.9232 | 731.2062
[12 empty] | 151 | 7157.6668 | 117.0426 | 777.1929
[12 empty] | 152 | 6824.7364 | 123.1805 | 538.5286
[12 empty] | 153 | 7863.8123 | 104.9541 | 932.3138
[12 empty] | 154 | 5868.2375 | 82.1801 | 867.5931
[12 empty] | 155 | 6412.8787 | 107.9871 | 1043.1648
[12 empty] | 156 | 7811.2887 | 85.0289 | 937.4352
[12 empty] | 157 | 6117.1729 | 86.8389 | 571.3123
[12 empty] | 158 | 6634.6278 | 90.7927 | 387.6136
[12 empty] | 159 | 6697.3266 | 107.9988 | 511.0252
[12 empty] | 160 | 6656.0208 | 98.4632 | 623.4519
[12 empty] | 161 | 5838.4683 | 91.167 | 823.1582
[12 empty] | 162 | 6215.1936 | 83.3972 | 603.4951
[12 empty] | 163 | 6650.6112 | 90.7558 | 628.1846
[12 empty] | 164 | 6079.7247 | 98.7244 | 479.5152
[12 empty] | 165 | 5281.3426 | 105.847 | 744.7461
[12 empty] | 166 | 5941.5514 | 110.3254 | 732.4915
[12 empty] | 167 | 7035.9703 | 110.2532 | 655.9823
[12 empty] | 168 | 7484.9882 | 80.2499 | 489.5976
[12 empty] | 169 | 5396.4549 | 76.8096 | 432.7011
[12 empty] | 170 | 5945.2457 | 108.2595 | 612.977
[12 empty] | 171 | 7356.0374 | 93.6075 | 999.0082
[12 empty] | 172 | 5768.9233 | 88.362 | 745.1154
[12 empty] | 173 | 7004.2412 | 115.7834 | 610.7761
[12 empty] | 174 | 6007.8608 | 98.3518 | 827.911
[12 empty] | 175 | 6860.5473 | 105.2791 | 798.3079
[12 empty] | 176 | 5668.8099 | 105.4926 | 756.8976
[12 empty] | 177 | 5628.8334 | 88.9044 | 761.0378
[12 empty] | 178 | 6873.0612 | 100.8 | 750.0166
[12 empty] | 179 | 6333.1936 | 104.2096 | 973.9331
[12 empty] | 180 | 5975.0767 | 104.1391 | 853.8634
[12 empty] | 181 | 7045.5555 | 122.0655 | 558.2082
[12 empty] | 182 | 5928.7507 | 89.1381 | 898.6205
[12 empty] | 183 | 6717.2946 | 103.2641 | 660.7498
[12 empty] | 184 | 6533.9174 | 99.6004 | 560.2864
[12 empty] | 185 | 5969.0262 | 85.6876 | 491.5523
[12 empty] | 186 | 6899.0768 | 105.807 | 885.5841
[12 empty] | 187 | 5328.6229 | 109.4324 | 605.2183
[12 empty] | 188 | 6622.4705 | 84.5263 | 736.9362
[12 empty] | 189 | 4799.551 | 95.5165 | 725.7912
[12 empty] | 190 | 6478.1852 | 100.2591 | 847.2853
[12 empty] | 191 | 4942.4975 | 105.7809 | 725.481
[12 empty] | 192 | 5437.7565 | 83.9771 | 471.3401
[12 empty] | 193 | 5174.9478 | 107.2128 | 843.2764
[12 empty] | 194 | 5570.2384 | 84.7226 | 754.0707
[12 empty] | 195 | 6539.2086 | 104.4104 | 582.3706
[12 empty] | 196 | 5894.3574 | 102.6234 | 850.1842
[12 empty] | 197 | 4962.3221 | 108.9833 | 437.4595
[12 empty] | 198 | 5089.999 | 96.6878 | 626.9537
[12 empty] | 199 | 6169.3293 | 92.663 | 476.8423
[12 empty] | 200 | 7149.6013 | 84.8997 | 573.8072
[12 empty] | 201 | 6351.7565 | 79.3125 | 741.9046
[12 empty] | 202 | 6336.3095 | 79.0105 | 803.1607
[12 empty] | 203 | 7237.0164 | 126.7634 | 679.8003
[12 empty] | 204 | 5519.4936 | 103.6114 | 711.3504
[12 empty] | 205 | 6732.6447 | 81.6708 | 696.9905
[12 empty] | 206 | 5320.1745 | 97.2145 | 777.8634
[12 empty] | 207 | 5551.1764 | 107.8954 | 563.6499
[12 empty] | 208 | 5432.4492 | 109.268 | 559.3315
[12 empty] | 209 | 5920.6011 | 95.783 | 919.112
[12 empty] | 210 | 6257.1805 | 113.4381 | 780.3645
[12 empty] | 211 | 5943.3908 | 98.8542 | 772.0005
[12 empty] | 212 | 6240.7625 | 105.2536 | 783.5105
[12 empty] | 213 | 4713.7231 | 94.4131 | 710.6318
[12 empty] | 214 | 6147.9704 | 110.802 | 724.0406
[12 empty] | 215 | 5751.1272 | 103.1634 | 739.4149
[12 empty] | 216 | 6002.3279 | 123.4773 | 802.3208
[12 empty] | 217 | 6725.2573 | 112.3521 | 618.1155
[12 empty] | 218 | 5118.9287 | 106.4716 | 551.2581
[12 empty] | 219 | 6290.2627 | 97.4599 | 893.2507
[12 empty] | 220 | 4745.7342 | 86.0299 | 723.6276
[12 empty] | 221 | 5630.4795 | 77.0985 | 672.8493
[12 empty] | 222 | 7688.8277 | 115.4359 | 614.9438
[12 empty] | 223 | 6516.6568 | 78.0998 | 683.4991
[12 empty] | 224 | 6297.9563 | 96.637 | 756.8827
[12 empty] | 225 | 4829.4103 | 102.5965 | 568.7149
[12 empty] | 226 | 5062.6983 | 84.613 | 751.5172
[12 empty] | 227 | 5502.3677 | 94.13 | 659.539
[12 empty] | 228 | 5708.7575 | 109.1361 | 919.504
[12 empty] | 229 | 5046.4207 | 93.2247 | 561.8123
[12 empty] | 230 | 7529.1362 | 105.8266 | 877.757
[12 empty] | 231 | 5779.0713 | 108.1627 | 528.233
[12 empty] | 232 | 6748.1693 | 95.083 | 756.318
[12 empty] | 233 | 7244.3033 | 90.5941 | 683.4657
[12 empty] | 234 | 5678.8659 | 91.231 | 529.2158
[12 empty] | 235 | 6689.1597 | 98.376 | 719.8398
[12 empty] | 236 | 5590.1001 | 110.7461 | 861.2075
[12 empty] | 237 | 6263.7218 | 66.575 | 508.867
[12 empty] | 238 | 6791.8437 | 116.7388 | 742.694
[12 empty] | 239 | 6703.1747 | 101.8156 | 1035.5258
[12 empty] | 240 | 6156.4049 | 99.7266 | 792.6598
[12 empty] | 241 | 5627.5983 | 119.6075 | 781.2424
[12 empty] | 242 | 5507.228 | 111.5253 | 827.2311
[12 empty] | 243 | 6414.9615 | 89.8896 | 588.1905
[12 empty] | 244 | 6184.6381 | 113.3838 | 592.467
[12 empty] | 245 | 6537.4328 | 76.2565 | 523.9521
[12 empty] | 246 | 5307.4682 | 83.9535 | 968.8819
[12 empty] | 247 | 5583.4822 | 89.5648 | 895.2052
[12 empty] | 248 | 5729.7912 | 99.1342 | 705.4629
[12 empty] | 249 | 6251.3067 | 84.5193 | 869.1683
[12 empty] | 250 | 6529.2601 | 97.6453 | 995.9309
[12 empty] | 251 | 6553.2435 | 111.5462 | 660.4248
[12 empty] | 252 | 5985.9556 | 109.3017 | 874.7894
[12 empty] | 253 | 6203.3403 | 108.9363 | 726.9136
[12 empty] | 254 | 4702.6633 | 104.4954 | 851.6729
[12 empty] | 255 | 5520.9531 | 101.7911 | 575.3696
[12 empty] | 256 | 7019.4472 | 88.4571 | 819.9768
[12 empty] | 257 | 6336.9116 | 87.249 | 576.1058
[12 empty] | 258 | 5525.3196 | 83.1078 | 793.2863
[12 empty] | 259 | 5313.251 | 97.4245 | 513.4744
[12 empty] | 260 | 7040.3023 | 113.4942 | 648.8172
[12 empty] | 261 | 7237.6555 | 81.3079 | 774.1003
[12 empty] | 262 | 4904.1126 | 113.1061 | 554.3009
[12 empty] | 263 | 5362.6118 | 97.7988 | 873.1518
[12 empty] | 264 | 6421.7654 | 85.6164 | 646.7851
[12 empty] | 265 | 6442.6901 | 80.8145 | 581.9651
[12 empty] | 266 | 6595.5287 | 108.5047 | 691.4012
[12 empty] | 267 | 7331.2883 | 74.6095 | 683.9145
[12 empty] | 268 | 5905.1072 | 89.2063 | 608.9213
[12 empty] | 269 | 6706.9085 | 97.4186 | 682.7872
[12 empty] | 270 | 5475.2752 | 114.0389 | 641.996
[12 empty] | 271 | 7272.1485 | 94.8767 | 542.7055
[12 empty] | 272 | 5894.9104 | 89.146 | 949.1848
[12 empty] | 273 | 5036.091 | 81.6027 | 789.5504
[12 empty] | 274 | 6655.0139 | 110.3014 | 701.3245
[12 empty] | 275 | 6058.0315 | 108.4642 | 776.7362
[12 empty] | 276 | 5746.8297 | 101.0651 | 649.6625
[12 empty] | 277 | 6188.4524 | 104.4572 | 993.306
[12 empty] | 278 | 6477.7033 | 109.1647 | 536.293
[12 empty] | 279 | 7520.6401 | 101.623 | 584.1218
[12 empty] | 280 | 6420.8707 | 107.188 | 707.8606
[12 empty] | 281 | 5568.641 | 73.6427 | 611.5928
[12 empty] | 282 | 6344.9671 | 85.6952 | 747.6895
[12 empty] | 283 | 4684.6166 | 94.9516 | 892.257
[12 empty] | 284 | 6234.1829 | 106.102 | 667.1573
[12 empty] | 285 | 6081.7997 | 116.9975 | 574.8338
[12 empty] | 286 | 5283.1248 | 96.3749 | 596.0927
[12 empty] | 287 | 5590.5452 | 97.5354 | 949.4792
[12 empty] | 288 | 6298.1907 | 94.3485 | 685.363
[12 empty] | 289 | 5869.6655 | 102.7561 | 459.643
[12 empty] | 290 | 4920.3138 | 90.7906 | 355.2187
[12 empty] | 291 | 5269.6307 | 87.2266 | 585.3267
[12 empty] | 292 | 6424.0635 | 101.2209 | 537.3675
[12 empty] | 293 | 6125.9441 | 90.2637 | 381.5496
[12 empty] | 294 | 6175.863 | 106.3774 | 793.5161
[12 empty] | 295 | 6670.5662 | 96.4319 | 643.4569
[12 empty] | 296 | 7353.3954 | 100.4126 | 628.3428
[12 empty] | 297 | 7129.9529 | 89.2543 | 645.4317
[12 empty] | 298 | 5757.6949 | 98.8366 | 745.1572
[12 empty] | 299 | 7218.4807 | 117.2455 | 688.2001
[12 empty] | 300 | 6289.7821 | 83.9518 | 900.8114
[12 empty] | 301 | 6453.4563 | 75.3032 | 907.0845
[12 empty] | 302 | 6594.1387 | 78.7495 | 783.4852
[12 empty] | 303 | 6346.195 | 110.1887 | 522.9769
[12 empty] | 304 | 5420.2794 | 100.1901 | 559.7447
[12 empty] | 305 | 5392.9913 | 88.5634 | 821.6393
[12 empty] | 306 | 5257.1857 | 90.6349 | 756.3655
[12 empty] | 307 | 5420.2095 | 83.3607 | 691.8221
[12 empty] | 308 | 6460.1909 | 84.1849 | 988.0308
[12 empty] | 309 | 6667.0443 | 121.5857 | 711.2842
[12 empty] | 310 | 7388.7103 | 99.1847 | 563.1438
[12 empty] | 311 | 5976.2574 | 71.2049 | 532.1962
[12 empty] | 312 | 5848.8988 | 106.1035 | 625.1404
[12 empty] | 313 | 6267.5231 | 103.884 | 550.2436
[12 empty] | 314 | 5712.9424 | 91.9818 | 730.7955
[12 empty] | 315 | 6866.8952 | 114.3664 | 454.0726
[12 empty] | 316 | 5072.7633 | 71.6175 | 874.9569
[12 empty] | 317 | 5864.6878 | 112.597 | 602.6067
[12 empty] | 318 | 5324.724 | 110.2392 | 706.417
[12 empty] | 319 | 6311.7704 | 87.2586 | 551.5757
[12 empty] | 320 | 6498.9124 | 84.8733 | 799.1533
[12 empty] | 321 | 6094.5454 | 94.8219 | 741.3207
[12 empty] | 322 | 5427.432 | 88.1282 | 779.3199
[12 empty] | 323 | 7435.4017 | 102.6131 | 807.4258
[12 empty] | 324 | 6980.9191 | 100.2197 | 628.8135
[12 empty] | 325 | 5997.1744 | 82.7288 | 791.4952
[12 empty] | 326 | 6212.7444 | 110.0717 | 637.3417
[12 empty] | 327 | 5233.8868 | 87.4425 | 820.2138
[12 empty] | 328 | 5040.6883 | 84.9356 | 678.1714
[12 empty] | 329 | 6875.9786 | 109.6448 | 738.7615
[12 empty] | 330 | 5556.3309 | 82.5488 | 730.2445
[12 empty] | 331 | 5824.8713 | 107.4086 | 462.2699
[12 empty] | 332 | 5705.8387 | 107.9645 | 642.5847
[12 empty] | 333 | 6096.7542 | 99.3578 | 504.5328
[12 empty] | 334 | 6438.8068 | 108.1758 | 524.2311
[12 empty] | 335 | 6518.2194 | 83.4035 | 693.8704
[12 empty] | 336 | 5286.9684 | 91.5533 | 706.3838
[12 empty] | 337 | 5507.7346 | 114.6918 | 640.8617
[12 empty] | 338 | 6540.6259 | 80.5919 | 654.1385
[12 empty] | 339 | 7204.0309 | 93.6506 | 503.1832
[12 empty] | 340 | 6370.5105 | 101.5062 | 652.6541
[12 empty] | 341 | 7129.9385 | 92.4709 | 684.6561
[12 empty] | 342 | 6669.2345 | 117.4658 | 581.572
[12 empty] | 343 | 6648.3004 | 95.0631 | 665.5485
[12 empty] | 344 | 5812.6924 | 100.2946 | 640.7523
[12 empty] | 345 | 6783.7622 | 92.4789 | 820.5671
[12 empty] | 346 | 7087.7535 | 91.6397 | 976.7307
[12 empty] | 347 | 5736.82 | 110.6997 | 724.1276
[12 empty] | 348 | 6690.1547 | 92.9028 | 765.1199
[12 empty] | 349 | 5234.7413 | 91.1451 | 624.7502
[12 empty] | 350 | 6352.2134 | 118.5129 | 503.1736
[12 empty] | 351 | 5587.1995 | 96.8697 | 816.04
[12 empty] | 352 | 6550.5512 | 106.6909 | 814.9426
[12 empty] | 353 | 7156.9818 | 91.0305 | 729.6536
[12 empty] | 354 | 6963.3847 | 83.0193 | 609.738
[12 empty] | 355 | 4596.4457 | 89.165 | 563.333
[12 empty] | 356 | 5904.7665 | 116.2665 | 885.2604
[12 empty] | 357 | 6766.1679 | 103.8922 | 570.5186
[12 empty] | 358 | 6190.7619 | 91.2286 | 604.7438
[12 empty] | 359 | 6186.9462 | 78.4681 | 736.5578
[12 empty] | 360 | 6478.9093 | 107.8005 | 708.5671
[12 empty] | 361 | 5997.4893 | 113.9153 | 851.3284
[12 empty] | 362 | 5921.5221 | 87.3497 | 698.7969
[12 empty] | 363 | 6383.0023 | 108.2256 | 641.8108
[12 empty] | 364 | 6522.8141 | 75.1708 | 628.2757
[12 empty] | 365 | 5448.4549 | 82.39 | 796.8639
[12 empty] | 366 | 7089.925 | 81.54 | 456.8767
[12 empty] | 367 | 5476.1094 | 97.3502 | 645.1885
[12 empty] | 368 | 5957.5036 | 84.8109 | 815.493
[12 empty] | 369 | 5627.6554 | 78.9563 | 638.7994
[12 empty] | 370 | 6578.5186 | 100.8193 | 749.1612
[12 empty] | 371 | 5944.76 | 104.4368 | 603.729
[12 empty] | 372 | 6718.4685 | 105.7888 | 669.412
[12 empty] | 373 | 6915.686 | 86.0828 | 796.237
[12 empty] | 374 | 7419.0211 | 97.4921 | 679.4574
[12 empty] | 375 | 6169.1207 | 91.2734 | 653.5994
[12 empty] | 376 | 6344.6081 | 111.5472 | 654.9946
[12 empty] | 377 | 5871.0488 | 82.3844 | 760.3311
[12 empty] | 378 | 7158.1729 | 72.4374 | 722.2386
[12 empty] | 379 | 5632.1468 | 90.5875 | 672.2598
[12 empty] | 380 | 6940.199 | 103.3253 | 743.9914
[12 empty] | 381 | 7102.4894 | 90.8037 | 622.1528
[12 empty] | 382 | 6442.5369 | 122.1369 | 490.4745
[12 empty] | 383 | 5651.58 | 88.3134 | 436.9196
[12 empty] | 384 | 5309.1412 | 78.9438 | 873.7685
[12 empty] | 385 | 5753.7215 | 109.3504 | 924.2282
[12 empty] | 386 | 6282.9012 | 105.1207 | 736.3989
[12 empty] | 387 | 4886.191 | 107.1463 | 878.2485
[12 empty] | 388 | 6040.7542 | 95.6529 | 613.2163
[12 empty] | 389 | 5776.3833 | 122.1909 | 721.3836
[12 empty] | 390 | 5483.6126 | 96.5962 | 603.866
[12 empty] | 391 | 7127.5483 | 89.5654 | 694.681
[12 empty] | 392 | 6520.7761 | 104.65 | 507.8006
[12 empty] | 393 | 6591.6791 | 92.825 | 631.6912
[12 empty] | 394 | 6988.9503 | 89.4852 | 563.6795
[12 empty] | 395 | 6641.0321 | 97.9795 | 836.8353
[12 empty] | 396 | 6845.6409 | 76.7109 | 553.9022
[12 empty] | 397 | 5459.279 | 100.6904 | 810.8047
[12 empty] | 398 | 5054.2652 | 81.3191 | 697.9013
[12 empty] | 399 | 4678.4426 | 88.0195 | 582.0107
[12 empty] | 400 | 6518.0222 | 106.5374 | 760.2389
[12 empty] | 401 | 6716.1699 | 105.845 | 834.0004
[12 empty] | 402 | 6134.5989 | 81.4402 | 698.1485
[12 empty] | 403 | 6383.1931 | 96.4556 | 548.5891
[12 empty] | 404 | 6310.8983 | 99.6783 | 646.6337
[12 empty] | 405 | 6974.7502 | 73.1122 | 715.2319
[12 empty] | 406 | 5665.04 | 80.7698 | 488.238
[12 empty] | 407 | 6286.8911 | 118.5684 | 532.5063
[12 empty] | 408 | 5804.7571 | 81.9049 | 433.8208
[12 empty] | 409 | 7958.6912 | 88.0248 | 781.5032
[12 empty] | 410 | 6184.3403 | 101.5808 | 806.5039
[12 empty] | 411 | 6339.8534 | 82.2406 | 686.2354
[12 empty] | 412 | 5640.7652 | 80.0792 | 845.6411
[12 empty] | 413 | 5554.5687 | 105.0751 | 900.0569
[12 empty] | 414 | 5741.4785 | 87.508 | 865.562
[12 empty] | 415 | 7693.4483 | 103.1974 | 828.3619
[12 empty] | 416 | 5531.7467 | 110.7384 | 746.4418
[12 empty] | 417 | 5788.2917 | 112.6927 | 682.9078
[12 empty] | 418 | 6094.7806 | 120.4616 | 755.9405
[12 empty] | 419 | 6187.2964 | 99.7739 | 617.3992
[12 empty] | 420 | 5902.4127 | 79.029 | 654.2647
[12 empty] | 421 | 7094.9624 | 116.7281 | 628.41
[12 empty] | 422 | 6391.3134 | 95.8497 | 585.8618
[12 empty] | 423 | 5904.1686 | 93.5848 | 639.9551
[12 empty] | 424 | 4875.1662 | 106.9296 | 897.4071
[12 empty] | 425 | 6170.8328 | 83.3701 | 781.7083
[12 empty] | 426 | 6136.6162 | 91.6324 | 861.5705
[12 empty] | 427 | 6452.2109 | 94.391 | 798.7038
[12 empty] | 428 | 5998.1062 | 98.9218 | 654.1422
[12 empty] | 429 | 5883.6053 | 97.8291 | 480.8456
[12 empty] | 430 | 5722.8862 | 90.802 | 844.5872
[12 empty] | 431 | 5853.3282 | 81.6404 | 713.1793
[12 empty] | 432 | 4941.0339 | 116.0754 | 655.1135
[12 empty] | 433 | 6587.6774 | 97.9759 | 545.8996
[12 empty] | 434 | 6566.8668 | 86.4184 | 521.4896
[12 empty] | 435 | 5511.6705 | 115.6669 | 595.359
[12 empty] | 436 | 6722.0608 | 101.1201 | 619.0886
[12 empty] | 437 | 6333.2616 | 101.7783 | 681.014
[12 empty] | 438 | 5761.2187 | 80.6811 | 853.2195
[12 empty] | 439 | 5717.8901 | 105.8007 | 828.5483
[12 empty] | 440 | 6489.9916 | 79.3153 | 599.8327
[12 empty] | 441 | 5779.5555 | 90.1293 | 815.6757
[12 empty] | 442 | 7450.397 | 102.9139 | 924.0591
[12 empty] | 443 | 4785.0351 | 94.8117 | 775.543
[12 empty] | 444 | 7652.0062 | 83.7036 | 530.8041
[12 empty] | 445 | 5906.6304 | 76.2865 | 544.2417
[12 empty] | 446 | 6331.2278 | 80.8674 | 740.5236
[12 empty] | 447 | 6151.0091 | 84.6858 | 421.0035
[12 empty] | 448 | 6189.734 | 96.9059 | 765.4467
[12 empty] | 449 | 7486.4235 | 92.3762 | 684.9114
[12 empty] | 450 | 5685.2819 | 76.4259 | 702.1366
[12 empty] | 451 | 5191.4316 | 118.1051 | 532.9113
[12 empty] | 452 | 6467.187 | 96.574 | 660.344
[12 empty] | 453 | 6891.5714 | 115.7651 | 767.9372
[12 empty] | 454 | 5379.7958 | 72.7445 | 899.4025
[12 empty] | 455 | 5729.6434 | 101.3532 | 421.8193
[12 empty] | 456 | 6908.5187 | 103.901 | 565.5725
[12 empty] | 457 | 5749.4644 | 97.0648 | 655.9611
[12 empty] | 458 | 6126.3531 | 92.3182 | 729.8745
[12 empty] | 459 | 6581.6232 | 95.6888 | 605.9407
[12 empty] | 460 | 5242.6034 | 72.1284 | 486.7541
[12 empty] | 461 | 6350.0153 | 97.8576 | 824.7101
[12 empty] | 462 | 6940.1238 | 118.3436 | 589.5695
[12 empty] | 463 | 4722.5791 | 115.2577 | 871.4118
[12 empty] | 464 | 5870.7928 | 97.0985 | 745.8134
[12 empty] | 465 | 5376.0582 | 99.4222 | 491.6446
[12 empty] | 466 | 7151.0722 | 86.8323 | 799.3156
[12 empty] | 467 | 5823.4452 | 86.8503 | 847.6137
[12 empty] | 468 | 5055.735 | 90.7462 | 657.7012
[12 empty] | 469 | 5253.299 | 95.2062 | 947.0169
[12 empty] | 470 | 7245.6481 | 95.2065 | 720.1984
[12 empty] | 471 | 6278.4049 | 89.4014 | 503.4187
[12 empty] | 472 | 5425.1143 | 103.9799 | 823.3248
[12 empty] | 473 | 5550.2942 | 91.2989 | 886.0906
[12 empty] | 474 | 6273.5703 | 77.8969 | 638.7674
[12 empty] | 475 | 7297.2178 | 85.9947 | 505.3557
[12 empty] | 476 | 5205.7656 | 101.1424 | 764.9464
[12 empty] | 477 | 6367.288 | 91.0712 | 629.287
[12 empty] | 478 | 5430.1412 | 121.6252 | 630.1292
[12 empty] | 479 | 5573.2028 | 115.0053 | 631.4505
[12 empty] | 480 | 5751.635 | 70.8297 | 772.3362
[12 empty] | 481 | 6286.9663 | 91.1955 | 556.5925
[12 empty] | 482 | 5946.2227 | 85.0314 | 712.9459
[12 empty] | 483 | 7373.2332 | 102.3904 | 661.7537
[12 empty] | 484 | 6643.1213 | 105.6164 | 685.8864
[12 empty] | 485 | 7170.4741 | 85.0996 | 645.7978
[12 empty] | 486 | 6015.3675 | 84.3137 | 690.1279
[12 empty] | 487 | 7053.3932 | 107.481 | 666.5343
[12 empty] | 488 | 6623.4541 | 92.9612 | 662.3794
[12 empty] | 489 | 6915.0385 | 115.0404 | 637.0587
[12 empty] | 490 | 5753.3277 | 80.3652 | 615.8767
[12 empty] | 491 | 7445.5067 | 102.4662 | 573.3353
[12 empty] | 492 | 6063.7198 | 80.346 | 496.204
[12 empty] | 493 | 5021.9778 | 83.3305 | 824.765
[12 empty] | 494 | 6423.073 | 89.1349 | 887.2597
[12 empty] | 495 | 6712.1474 | 102.6362 | 377.0568
[12 empty] | 496 | 5708.2053 | 95.6884 | 554.807
[12 empty] | 497 | 6532.5378 | 81.7339 | 674.5759
[12 empty] | 498 | 6283.5116 | 113.6531 | 575.9119
[12 empty] | 499 | 5946.4392 | 74.842 | 882.672
[12 empty] | 500 | 5411.3841 | 106.1793 | 784.2183
[12 empty] | 501 | 7549.1781 | 118.7902 | 735.7475
[12 empty] | 502 | 5841.3308 | 78.5823 | 665.5759
[12 empty] | 503 | 7212.6562 | 81.37 | 663.8432
[12 empty] | 504 | 6308.3585 | 116.2557 | 916.5794
[12 empty] | 505 | 7468.0133 | 109.5994 | 898.881
[12 empty] | 506 | 6302.4888 | 88.7068 | 747.7526
[12 empty] | 507 | 6269.2593 | 89.0135 | 447.5043
[12 empty] | 508 | 5478.9981 | 105.3501 | 710.2123
[12 empty] | 509 | 5506.1904 | 101.6362 | 746.7167
[12 empty] | 510 | 6182.128 | 108.625 | 819.1854
[12 empty] | 511 | 6065.7071 | 110.2312 | 710.6937
[12 empty] | 512 | 6028.393 | 82.6164 | 684.1543
[12 empty] | 513 | 5544.8791 | 87.2572 | 797.1943
[12 empty] | 514 | 5612.0171 | 84.3736 | 555.2453
[12 empty] | 515 | 6704.5832 | 93.6421 | 649.3085
[12 empty] | 516 | 6441.3989 | 84.4923 | 758.4933
[12 empty] | 517 | 7007.2047 | 98.4622 | 609.0856
[12 empty] | 518 | 5227.2441 | 80.6418 | 828.6319
[12 empty] | 519 | 6843.4674 | 97.7034 | 614.2209
[12 empty] | 520 | 6971.5695 | 112.4865 | 763.0624
[12 empty] | 521 | 6013.9629 | 106.4793 | 671.5792
[12 empty] | 522 | 5450.1285 | 104.5214 | 719.1105
[12 empty] | 523 | 6859.2604 | 96.2163 | 658.9331
[12 empty] | 524 | 5801.1616 | 99.4794 | 866.2943
[12 empty] | 525 | 5754.4327 | 92.0708 | 670.6653
[12 empty] | 526 | 6862.3249 | 70.0881 | 682.5275
[12 empty] | 527 | 5993.3619 | 100.4697 | 711.5892
[12 empty] | 528 | 6314.2771 | 97.8206 | 743.2786
[12 empty] | 529 | 6252.5438 | 109.7076 | 633.1857
[12 empty] | 530 | 4669.2988 | 69.3945 | 881.1708
[12 empty] | 531 | 6328.072 | 101.2652 | 520.1995
[12 empty] | 532 | 5694.068 | 107.4041 | 685.4288
[12 empty] | 533 | 5372.5212 | 115.6775 | 739.9257
[12 empty] | 534 | 7646.3421 | 78.1681 | 518.8609
[12 empty] | 535 | 4699.935 | 82.9811 | 991.1286
[12 empty] | 536 | 5694.9937 | 97.2999 | 577.2491
[12 empty] | 537 | 5697.9319 | 97.5469 | 856.0229
[12 empty] | 538 | 7057.2457 | 100.6778 | 597.8769
[12 empty] | 539 | 5961.3734 | 90.4496 | 498.5775
[12 empty] | 540 | 5291.409 | 90.6699 | 692.1062
[12 empty] | 541 | 5556.0727 | 106.5346 | 605.5561
[12 empty] | 542 | 5931.1057 | 95.5305 | 571.84
[12 empty] | 543 | 6354.0942 | 96.9602 | 900.6227
[12 empty] | 544 | 5646.2543 | 94.0376 | 560.936
[12 empty] | 545 | 6811.4581 | 109.1659 | 545.4718
[12 empty] | 546 | 5858.7238 | 104.8428 | 808.6612
[12 empty] | 547 | 7361.2119 | 103.0021 | 655.2051
[12 empty] | 548 | 6129.9428 | 71.8532 | 412.865
[12 empty] | 549 | 6192.3129 | 79.0257 | 532.5688
[12 empty] | 550 | 5525.5129 | 98.7714 | 489.8924
[12 empty] | 551 | 5594.4228 | 90.9295 | 527.964
[12 empty] | 552 | 6422.7868 | 90.0873 | 841.6196
[12 empty] | 553 | 6198.0398 | 95.7924 | 674.364
[12 empty] | 554 | 5944.4209 | 82.1433 | 517.0825
[12 empty] | 555 | 6737.6922 | 100.041 | 731.689
[12 empty] | 556 | 6590.7525 | 88.5518 | 700.1855
[12 empty] | 557 | 6858.1761 | 71.6322 | 588.7575
[12 empty] | 558 | 5215.7559 | 110.387 | 582.0408
[12 empty] | 559 | 5558.8538 | 107.5055 | 676.6645
[12 empty] | 560 | 6109.5935 | 96.7407 | 536.6334
[12 empty] | 561 | 7242.967 | 96.2782 | 526.824
[12 empty] | 562 | 6361.631 | 76.1252 | 675.47
[12 empty] | 563 | 6906.9477 | 97.2413 | 656.8614
[12 empty] | 564 | 6273.6226 | 100.4579 | 824.6389
[12 empty] | 565 | 6046.9441 | 107.4344 | 687.1106
[12 empty] | 566 | 4768.7051 | 77.354 | 866.7021
[12 empty] | 567 | 6273.665 | 112.1208 | 531.8318
[12 empty] | 568 | 5074.5211 | 109.2628 | 751.3234
[12 empty] | 569 | 6717.4393 | 95.4694 | 808.7218
[12 empty] | 570 | 7717.9352 | 106.6838 | 751.8388
[12 empty] | 571 | 5837.5986 | 103.7566 | 702.473
[12 empty] | 572 | 7187.1606 | 73.5858 | 773.6693
[12 empty] | 573 | 5549.0074 | 107.311 | 638.4279
[12 empty] | 574 | 6633.4092 | 88.0719 | 675.7933
[12 empty] | 575 | 5937.0676 | 106.0216 | 704.8586
[12 empty] | 576 | 7377.8674 | 110.508 | 820.7798
[12 empty] | 577 | 5133.0029 | 107.7796 | 630.4004
[12 empty] | 578 | 5704.2483 | 118.4872 | 534.4185
[12 empty] | 579 | 4664.5742 | 79.0442 | 527.4586
[12 empty] | 580 | 6519.2564 | 112.1304 | 676.263
[12 empty] | 581 | 6420.8263 | 78.2541 | 701.6154
[12 empty] | 582 | 7452.0766 | 108.7777 | 822.8926
[12 empty] | 583 | 6292.0556 | 111.6179 | 727.0836
[12 empty] | 584 | 6324.1852 | 84.7467 | 693.1484
[12 empty] | 585 | 7064.7255 | 98.8676 | 809.3534
[12 empty] | 586 | 6158.4269 | 111.6942 | 673.5886
[12 empty] | 587 | 5022.0023 | 84.6553 | 532.8314
[12 empty] | 588 | 5931.9478 | 75.1786 | 469.9093
[12 empty] | 589 | 6516.2843 | 98.6465 | 871.426
[12 empty] | 590 | 6362.8222 | 87.5401 | 523.3764
[12 empty] | 591 | 5586.4308 | 95.2361 | 785.1127
[12 empty] | 592 | 6204.8942 | 86.9183 | 702.4691
[12 empty] | 593 | 6555.2778 | 72.4255 | 532.7955
[12 empty] | 594 | 6286.0423 | 74.7746 | 835.1677
[12 empty] | 595 | 5603.1556 | 104.6424 | 648.7996
[12 empty] | 596 | 6542.659 | 119.3444 | 698.1489
[12 empty] | 597 | 6832.9398 | 116.5546 | 702.6829
[12 empty] | 598 | 6596.7906 | 87.9768 | 690.3288
[12 empty] | 599 | 5682.7631 | 90.8138 | 871.4674
[12 empty] | 600 | 6595.444 | 84.7109 | 850.152
[12 empty] | 601 | 6187.7299 | 110.5957 | 580.7107
[12 empty] | 602 | 6342.1312 | 98.4382 | 688.9016
[12 empty] | 603 | 6381.3065 | 81.3053 | 534.3681
[12 empty] | 604 | 5289.0891 | 91.1454 | 540.4558
[12 empty] | 605 | 5409.6847 | 114.7431 | 484.917
[12 empty] | 606 | 6906.7127 | 109.3462 | 681.898
[12 empty] | 607 | 5814.864 | 104.9556 | 776.8248
[12 empty] | 608 | 5680.4702 | 95.2867 | 923.6725
[12 empty] | 609 | 5875.1999 | 96.9349 | 670.6543
[12 empty] | 610 | 5539.361 | 125.5353 | 965.9633
[12 empty] | 611 | 5999.5321 | 80.6522 | 461.8254
[12 empty] | 612 | 6238.9429 | 77.7856 | 588.0543
[12 empty] | 613 | 5511.6133 | 114.1173 | 796.9927
[12 empty] | 614 | 6847.4535 | 81.7036 | 685.9788
[12 empty] | 615 | 6476.0911 | 87.9576 | 767.7597
[12 empty] | 616 | 5258.1302 | 105.9187 | 883.6884
[12 empty] | 617 | 5644.9346 | 105.0221 | 746.7732
[12 empty] | 618 | 6021.8287 | 91.8107 | 707.384
[12 empty] | 619 | 7350.47 | 100.5424 | 617.8683
[12 empty] | 620 | 4502.9282 | 106.4532 | 799.4695
[12 empty] | 621 | 6081.7012 | 79.7144 | 481.5281
[12 empty] | 622 | 5543.4 | 91.1923 | 973.4695
[12 empty] | 623 | 6731.709 | 82.0011 | 597.6014
[12 empty] | 624 | 5529.2824 | 88.8026 | 479.1087
[12 empty] | 625 | 5416.5303 | 98.4055 | 680.3776
[12 empty] | 626 | 6650.0639 | 85.6958 | 796.334
[12 empty] | 627 | 5468.9946 | 87.5501 | 825.8153
[12 empty] | 628 | 7220.925 | 101.4419 | 875.0253
[12 empty] | 629 | 6367.6425 | 81.2862 | 638.909
[12 empty] | 630 | 5644.7539 | 70.489 | 667.2455
[12 empty] | 631 | 6217.35 | 97.9141 | 764.861
[12 empty] | 632 | 6868.0831 | 92.9679 | 589.2998
[12 empty] | 633 | 5518.3059 | 68.2533 | 810.4795
[12 empty] | 634 | 6340.8991 | 84.8965 | 542.6815
[12 empty] | 635 | 7272.4222 | 97.5288 | 407.3009
[12 empty] | 636 | 5566.94 | 79.4289 | 813.4856
[12 empty] | 637 | 5719.3088 | 108.4495 | 632.0317
[12 empty] | 638 | 5819.4585 | 99.9023 | 805.5205
[12 empty] | 639 | 5317.0389 | 102.3278 | 692.6329
[12 empty] | 640 | 6518.7433 | 102.1811 | 704.0905
[12 empty] | 641 | 6574.2743 | 124.1159 | 660.7416
[12 empty] | 642 | 5848.7919 | 114.7329 | 878.1894
[12 empty] | 643 | 6697.746 | 99.6985 | 627.8809
[12 empty] | 644 | 5743.6484 | 95.0777 | 559.5261
[12 empty] | 645 | 4497.5669 | 85.7745 | 581.7352
[12 empty] | 646 | 5926.4478 | 114.5595 | 703.6437
[12 empty] | 647 | 5504.3709 | 116.5917 | 940.9927
[12 empty] | 648 | 6673.4747 | 88.3974 | 572.3993
[12 empty] | 649 | 6254.8468 | 105.9371 | 858.3747
[12 empty] | 650 | 4819.7487 | 110.7686 | 547.7768
[12 empty] | 651 | 5024.6502 | 91.3418 | 611.0273
[12 empty] | 652 | 4977.228 | 107.3938 | 841.508
[12 empty] | 653 | 7295.6997 | 97.364 | 587.089
[12 empty] | 654 | 7301.4848 | 97.1338 | 777.2701
[12 empty] | 655 | 6507.5849 | 77.9773 | 942.469
[12 empty] | 656 | 7088.1837 | 80.2503 | 619.7249
[12 empty] | 657 | 6161.3235 | 119.8561 | 688.7707
[12 empty] | 658 | 7184.5725 | 89.9065 | 627.5853
[12 empty] | 659 | 5773.248 | 107.3836 | 849.7688
[12 empty] | 660 | 6763.8722 | 81.418 | 705.313
[12 empty] | 661 | 6789.6819 | 89.3546 | 782.6448
[12 empty] | 662 | 6848.2094 | 79.3477 | 880.1305
[12 empty] | 663 | 6098.765 | 88.8313 | 806.727
[12 empty] | 664 | 6416.9736 | 88.6345 | 781.498
[12 empty] | 665 | 6533.6077 | 119.4462 | 887.237
[12 empty] | 666 | 7523.621 | 92.6369 | 752.7913
[12 empty] | 667 | 5871.0428 | 90.5268 | 556.2432
[12 empty] | 668 | 5928.9486 | 99.6596 | 922.9838
[12 empty] | 669 | 6264.078 | 102.4684 | 491.0738
[12 empty] | 670 | 7097.3665 | 90.0219 | 896.0428
[12 empty] | 671 | 7433.093 | 98.5089 | 849.7431
[12 empty] | 672 | 7107.5009 | 77.0931 | 825.4475
[12 empty] | 673 | 6662.6811 | 115.2402 | 393.3848
[12 empty] | 674 | 7283.4656 | 105.634 | 809.8276
[12 empty] | 675 | 6903.1835 | 100.782 | 610.3336
[12 empty] | 676 | 6427.0652 | 75.5194 | 869.7403
[12 empty] | 677 | 7218.8526 | 90.6105 | 772.8303
[12 empty] | 678 | 6194.8623 | 108.7825 | 802.1926
[12 empty] | 679 | 5153.2795 | 81.8357 | 793.4494
[12 empty] | 680 | 5913.9143 | 83.6171 | 620.1104
[12 empty] | 681 | 7228.9272 | 94.6472 | 758.6605
[12 empty] | 682 | 4762.137 | 92.5912 | 804.2505
[12 empty] | 683 | 6041.2528 | 124.3635 | 443.98
[12 empty] | 684 | 5428.5927 | 89.6087 | 535.526
[12 empty] | 685 | 6004.0082 | 99.9689 | 516.5175
[12 empty] | 686 | 6060.0535 | 98.8447 | 729.2672
[12 empty] | 687 | 6912.3228 | 111.0769 | 575.6114
[12 empty] | 688 | 6176.2887 | 88.1856 | 528.2797
[12 empty] | 689 | 5668.7619 | 114.7269 | 730.7019
[12 empty] | 690 | 5710.946 | 86.7894 | 669.5946
[12 empty] | 691 | 6690.747 | 91.9175 | 741.3901
[12 empty] | 692 | 5915.5273 | 96.1783 | 708.2475
[12 empty] | 693 | 4673.3667 | 96.3247 | 847.0142
[12 empty] | 694 | 6892.0759 | 114.0255 | 804.0797
[12 empty] | 695 | 6414.9485 | 96.1124 | 483.2678
[12 empty] | 696 | 7462.5663 | 82.6046 | 527.5379
[12 empty] | 697 | 5439.1501 | 86.478 | 511.3822
[12 empty] | 698 | 6028.8779 | 76.8578 | 753.2009
[12 empty] | 699 | 5813.8446 | 85.7381 | 713.5357
[12 empty] | 700 | 4756.2651 | 100.8267 | 689.3656
[12 empty] | 701 | 6670.9668 | 93.206 | 724.7036
[12 empty] | 702 | 5773.3368 | 82.6524 | 668.1564
[12 empty] | 703 | 5635.1547 | 100.8567 | 686.6551
[12 empty] | 704 | 7012.4198 | 93.9713 | 662.8286
[12 empty] | 705 | 5965.1368 | 117.3477 | 929.8953
[12 empty] | 706 | 5618.5418 | 100.2044 | 596.5673
[12 empty] | 707 | 6501.0837 | 100.2044 | 562.7524
[12 empty] | 708 | 6831.9375 | 86.9848 | 482.4507
[12 empty] | 709 | 4714.887 | 80.3694 | 561.0463
[12 empty] | 710 | 6794.9369 | 103.7206 | 825.693
[12 empty] | 711 | 6651.5555 | 80.885 | 1006.5057
[12 empty] | 712 | 5930.1893 | 109.6315 | 709.1127
[12 empty] | 713 | 5746.7585 | 114.3463 | 888.5451
[12 empty] | 714 | 6123.7731 | 102.1169 | 635.5302
[12 empty] | 715 | 6758.2259 | 79.5054 | 543.0215
[12 empty] | 716 | 7438.7959 | 106.627 | 550.0214
[12 empty] | 717 | 6413.5672 | 77.2506 | 516.9349
[12 empty] | 718 | 5948.2789 | 93.5591 | 781.2485
[12 empty] | 719 | 6543.4395 | 103.5272 | 691.8865
[12 empty] | 720 | 6063.3757 | 98.493 | 647.9794
[12 empty] | 721 | 6121.7853 | 108.6581 | 635.1078
[12 empty] | 722 | 6382.7357 | 104.452 | 657.0639
[12 empty] | 723 | 6825.3866 | 89.1666 | 656.3147
[12 empty] | 724 | 5649.376 | 113.098 | 880.3428
[12 empty] | 725 | 5782.3693 | 85.1241 | 751.7664
[12 empty] | 726 | 6387.3856 | 97.3509 | 680.7756
[12 empty] | 727 | 6308.0436 | 99.7663 | 814.0786
[12 empty] | 728 | 7714.8697 | 113.2455 | 670.4932
[12 empty] | 729 | 6159.5921 | 90.4651 | 674.9646
[12 empty] | 730 | 5866.0955 | 113.1952 | 640.7785
[12 empty] | 731 | 6007.3899 | 85.1289 | 713.7452
[12 empty] | 732 | 5882.4554 | 102.9449 | 831.3607
[12 empty] | 733 | 5122.9937 | 91.6623 | 647.6753
[12 empty] | 734 | 6214.5557 | 91.9608 | 452.8359
[12 empty] | 735 | 6145.0872 | 112.3582 | 794.2254
[12 empty] | 736 | 6530.8964 | 107.868 | 702.2216
[12 empty] | 737 | 6599.7593 | 96.6591 | 761.5068
[12 empty] | 738 | 5953.4838 | 110.0104 | 756.1246
[12 empty] | 739 | 7014.9371 | 88.7443 | 794.6359
[12 empty] | 740 | 5779.1845 | 86.0548 | 733.285
[12 empty] | 741 | 6959.4901 | 83.4206 | 601.7061
[12 empty] | 742 | 7511.1445 | 117.1655 | 477.9017
[12 empty] | 743 | 5220.0662 | 113.0128 | 716.4792
[12 empty] | 744 | 6847.8054 | 87.0742 | 548.2447
[12 empty] | 745 | 5060.8509 | 83.088 | 833.075
[12 empty] | 746 | 5860.6251 | 90.7149 | 704.3909
[12 empty] | 747 | 5326.7579 | 104.2084 | 813.244
[12 empty] | 748 | 7168.1831 | 108.3453 | 620.7422
[12 empty] | 749 | 6433.7167 | 110.3084 | 649.8517
[12 empty] | 750 | 5255.6527 | 106.016 | 657.8861
[12 empty] | 751 | 5254.0076 | 103.4362 | 624.1361
[12 empty] | 752 | 5363.5348 | 97.1242 | 564.6722
[12 empty] | 753 | 5819.2319 | 107.8303 | 382.5846
[12 empty] | 754 | 6459.6723 | 111.6221 | 756.8862
[12 empty] | 755 | 6024.7859 | 99.3898 | 810.3326
[12 empty] | 756 | 5217.9999 | 101.16 | 865.1436
[12 empty] | 757 | 6055.2867 | 79.9942 | 612.2855
[12 empty] | 758 | 5482.1098 | 111.2407 | 677.9023
[12 empty] | 759 | 6030.4615 | 78.4714 | 497.1294
[12 empty] | 760 | 6072.257 | 116.3812 | 642.3933
[12 empty] | 761 | 5572.5094 | 110.0159 | 671.8853
[12 empty] | 762 | 4469.9891 | 108.2282 | 540.7031
[12 empty] | 763 | 6396.8266 | 81.8996 | 455.2789
[12 empty] | 764 | 5373.4435 | 104.3561 | 688.9593
[12 empty] | 765 | 4950.6526 | 87.4751 | 942.5074
[12 empty] | 766 | 5128.8552 | 76.1665 | 753.6319
[12 empty] | 767 | 6163.2655 | 100.0616 | 605.0055
[12 empty] | 768 | 6485.8205 | 73.2282 | 641.6703
[12 empty] | 769 | 6792.9064 | 93.5901 | 716.884
[12 empty] | 770 | 5500.7195 | 107.5905 | 704.4057
[12 empty] | 771 | 7146.6796 | 100.4949 | 561.8264
[12 empty] | 772 | 7176.0356 | 93.1339 | 910.9808
[12 empty] | 773 | 5679.6445 | 82.1475 | 517.2296
[12 empty] | 774 | 6042.3964 | 103.5674 | 820.857
[12 empty] | 775 | 6292.4765 | 122.4366 | 570.0584
[12 empty] | 776 | 6070.4172 | 87.6901 | 691.0022
[12 empty] | 777 | 5365.7226 | 95.4672 | 706.4132
[12 empty] | 778 | 5866.2842 | 74.4032 | 640.7053
[12 empty] | 779 | 6480.7355 | 109.5727 | 846.088
[12 empty] | 780 | 4763.7506 | 78.9365 | 542.9469
[12 empty] | 781 | 5616.6898 | 88.0647 | 785.2227
[12 empty] | 782 | 6871.8854 | 98.1439 | 649.4599
[12 empty] | 783 | 5211.7634 | 105.5668 | 664.8968
[12 empty] | 784 | 6086.0264 | 107.0517 | 588.6969
[12 empty] | 785 | 5764.472 | 98.2477 | 611.4355
[12 empty] | 786 | 6348.7504 | 76.4231 | 664.0137
[12 empty] | 787 | 7272.8162 | 113.3106 | 512.1845
[12 empty] | 788 | 5630.4003 | 106.3466 | 690.1206
[12 empty] | 789 | 6897.8152 | 108.4135 | 663.2156
[12 empty] | 790 | 5802.321 | 116.9973 | 693.2211
[12 empty] | 791 | 6528.79 | 81.1058 | 752.1633
[12 empty] | 792 | 6209.7394 | 103.9898 | 673.6602
[12 empty] | 793 | 6023.8169 | 69.4119 | 499.6239
[12 empty] | 794 | 6223.0822 | 80.2895 | 696.0944
[12 empty] | 795 | 7243.8008 | 91.0283 | 729.9337
[12 empty] | 796 | 6788.1919 | 94.8856 | 558.4238
[12 empty] | 797 | 6253.2466 | 96.5373 | 870.9013
[12 empty] | 798 | 6413.1942 | 92.7157 | 545.0628
[12 empty] | 799 | 6581.5375 | 108.2284 | 474.4462
[12 empty] | 800 | 5899.2786 | 98.2795 | 765.0772
[12 empty] | 801 | 6917.0846 | 96.4386 | 447.6439
[12 empty] | 802 | 7112.1481 | 87.4287 | 627.752
[12 empty] | 803 | 6456.6306 | 108.3651 | 679.5139
[12 empty] | 804 | 6610.4816 | 124.6317 | 793.7727
[12 empty] | 805 | 7279.4292 | 111.6371 | 750.0731
[12 empty] | 806 | 6080.3472 | 77.1502 | 680.4385
[12 empty] | 807 | 7338.7949 | 89.1306 | 720.7095
[12 empty] | 808 | 7818.7443 | 98.7603 | 823.0948
[12 empty] | 809 | 6603.9659 | 82.8193 | 914.1485
[12 empty] | 810 | 7070.9783 | 88.3643 | 725.3833
[12 empty] | 811 | 6576.7803 | 94.8798 | 774.9547
[12 empty] | 812 | 6922.0384 | 105.5218 | 627.6718
[12 empty] | 813 | 7404.0297 | 84.931 | 717.7143
[12 empty] | 814 | 7771.6287 | 95.2942 | 699.9287
[12 empty] | 815 | 5643.2528 | 82.6583 | 749.5486
[12 empty] | 816 | 7122.7739 | 110.7199 | 790.3144
[12 empty] | 817 | 4944.3216 | 94.3845 | 744.6061
[12 empty] | 818 | 4745.0202 | 87.891 | 702.2053
[12 empty] | 819 | 6282.8974 | 99.8902 | 659.8946
[12 empty] | 820 | 7068.6342 | 107.9412 | 710.973
[12 empty] | 821 | 7156.6363 | 77.3165 | 698.6642
[12 empty] | 822 | 5852.2392 | 106.3363 | 675.2193
[12 empty] | 823 | 5600.6925 | 71.9141 | 686.1433
[12 empty] | 824 | 5491.1641 | 76.887 | 495.3943
[12 empty] | 825 | 4589.6239 | 106.9623 | 624.2925
[12 empty] | 826 | 5627.0432 | 108.9414 | 566.2535
[12 empty] | 827 | 5307.0665 | 88.4951 | 693.394
[12 empty] | 828 | 6142.3272 | 119.5276 | 789.6333
[12 empty] | 829 | 5715.6273 | 93.7235 | 830.7064
[12 empty] | 830 | 5520.7811 | 115.7076 | 474.5273
[12 empty] | 831 | 6672.4105 | 118.5822 | 694.5288
[12 empty] | 832 | 7261.7991 | 78.2041 | 663.4852
[12 empty] | 833 | 5854.8348 | 98.2381 | 756.3948
[12 empty] | 834 | 5591.5243 | 105.6514 | 826.4131
[12 empty] | 835 | 4947.8706 | 102.5646 | 754.8721
[12 empty] | 836 | 5445.2374 | 85.3444 | 877.3489
[12 empty] | 837 | 6885.4932 | 85.8418 | 752.878
[12 empty] | 838 | 6888.999 | 113.1636 | 707.4206
[12 empty] | 839 | 5031.6351 | 103.0847 | 544.4504
[12 empty] | 840 | 5547.6779 | 98.3222 | 953.6116
[12 empty] | 841 | 5403.0958 | 99.0048 | 840.3054
[12 empty] | 842 | 7208.5924 | 110.2749 | 606.9002
[12 empty] | 843 | 5001.9175 | 114.5793 | 873.4405
[12 empty] | 844 | 6217.9398 | 102.6611 | 841.8316
[12 empty] | 845 | 5235.6243 | 84.9296 | 644.8265
[12 empty] | 846 | 7123.9737 | 89.3037 | 885.0238
[12 empty] | 847 | 5661.3267 | 109.6964 | 916.9668
[12 empty] | 848 | 7690.1699 | 74.953 | 770.8149
[12 empty] | 849 | 5141.856 | 110.3164 | 715.7168
[12 empty] | 850 | 5451.3301 | 96.0239 | 740.1969
[12 empty] | 851 | 5601.708 | 88.1175 | 920.0948
[12 empty] | 852 | 5467.5579 | 93.3022 | 668.535
[12 empty] | 853 | 6139.0764 | 108.0928 | 608.9058
[12 empty] | 854 | 6359.5365 | 96.8478 | 834.8585
[12 empty] | 855 | 5401.785 | 100.6227 | 535.7219
[12 empty] | 856 | 5701.5721 | 114.8545 | 614.741
[12 empty] | 857 | 7049.9767 | 86.3251 | 882.7306
[12 empty] | 858 | 5952.8522 | 108.2196 | 536.0858
[12 empty] | 859 | 6221.9951 | 85.641 | 764.2028
[12 empty] | 860 | 5735.2446 | 65.3249 | 856.9554
[12 empty] | 861 | 4921.3401 | 92.5731 | 864.6893
[12 empty] | 862 | 7227.9376 | 77.623 | 751.7429
[12 empty] | 863 | 7275.8301 | 88.3239 | 756.1272
[12 empty] | 864 | 6773.5366 | 102.2815 | 656.9177
[12 empty] | 865 | 5920.4149 | 95.4646 | 808.8877
[12 empty] | 866 | 6065.3369 | 72.8199 | 516.1523
[12 empty] | 867 | 6621.2842 | 92.622 | 507.0224
[12 empty] | 868 | 5499.4712 | 82.3985 | 746.5771
[12 empty] | 869 | 6395.8691 | 119.9495 | 904.5983
[12 empty] | 870 | 5442.1385 | 76.6641 | 659.2869
[12 empty] | 871 | 7213.6 | 114.3357 | 821.0235
[12 empty] | 872 | 5898.374 | 92.8019 | 552.8393
[12 empty] | 873 | 5144.952 | 105.9704 | 847.6587
[12 empty] | 874 | 6334.8078 | 78.3957 | 687.1314
[12 empty] | 875 | 5250.6712 | 98.0425 | 575.6315
[12 empty] | 876 | 5571.0659 | 96.6329 | 873.2713
[12 empty] | 877 | 6368.9762 | 96.7854 | 730.1646
[12 empty] | 878 | 7063.8437 | 110.7008 | 843.7465
[12 empty] | 879 | 6198.3454 | 79.334 | 586.0734
[12 empty] | 880 | 6461.9092 | 104.3171 | 944.8308
[12 empty] | 881 | 6519.3864 | 104.5386 | 716.8063
[12 empty] | 882 | 5653.3226 | 103.6557 | 752.0569
[12 empty] | 883 | 7283.4343 | 92.8914 | 624.8433
[12 empty] | 884 | 6361.313 | 98.8172 | 692.6054
[12 empty] | 885 | 5235.2008 | 111.301 | 938.2279
[12 empty] | 886 | 6404.109 | 96.68 | 854.2653
[12 empty] | 887 | 6683.7019 | 79.2645 | 880.3126
[12 empty] | 888 | 5351.1124 | 108.0188 | 750.5744
[12 empty] | 889 | 6491.2234 | 85.4484 | 876.6513
[12 empty] | 890 | 4876.5595 | 104.0262 | 643.0709
[12 empty] | 891 | 5470.5801 | 114.2544 | 728.3058
[12 empty] | 892 | 6543.0746 | 104.7731 | 796.0772
[12 empty] | 893 | 6507.8076 | 122.4993 | 733.8809
[12 empty] | 894 | 5898.6828 | 92.562 | 613.7056
[12 empty] | 895 | 6201.0911 | 93.1512 | 667.8246
[12 empty] | 896 | 6916.5603 | 104.807 | 882.6732
[12 empty] | 897 | 7306.2869 | 80.4141 | 855.7054
[12 empty] | 898 | 6954.8158 | 105.3447 | 752.7729
[12 empty] | 899 | 5375.6138 | 106.5767 | 611.9604
[12 empty] | 900 | 7490.8152 | 115.0563 | 787.768
[12 empty] | 901 | 5446.0618 | 74.4562 | 628.4766
[12 empty] | 902 | 6861.5444 | 116.9701 | 979.4034
[12 empty] | 903 | 5552.9688 | 91.4806 | 730.3281
[12 empty] | 904 | 7200.5066 | 108.4911 | 654.9627
[12 empty] | 905 | 6985.3706 | 84.3349 | 621.8491
[12 empty] | 906 | 6261.7925 | 113.619 | 919.7252
[12 empty] | 907 | 6357.5914 | 104.6936 | 728.8466
[12 empty] | 908 | 4774.5397 | 84.2386 | 686.4297
[12 empty] | 909 | 7163.5556 | 91.4997 | 761.8786
[12 empty] | 910 | 5801.8812 | 92.7476 | 587.0919
[12 empty] | 911 | 5904.9042 | 108.9654 | 527.8146
[12 empty] | 912 | 5461.8759 | 93.7628 | 755.6529
[12 empty] | 913 | 4982.4849 | 105.2471 | 705.7349
[12 empty] | 914 | 5487.404 | 105.0142 | 603.7691
[12 empty] | 915 | 6137.113 | 118.6783 | 680.5408
[12 empty] | 916 | 6282.7082 | 85.3811 | 628.1729
[12 empty] | 917 | 6902.3939 | 77.63 | 662.8653
[12 empty] | 918 | 5687.7116 | 113.508 | 998.1029
[12 empty] | 919 | 6822.2935 | 77.0917 | 846.2388
[12 empty] | 920 | 7379.4993 | 100.8723 | 764.7374
[12 empty] | 921 | 6194.4444 | 73.0855 | 722.2371
[12 empty] | 922 | 7223.6466 | 113.8687 | 666.8672
[12 empty] | 923 | 6237.8217 | 92.4145 | 515.637
[12 empty] | 924 | 5988.3592 | 85.2757 | 609.5519
[12 empty] | 925 | 6341.6643 | 75.3712 | 739.0554
[12 empty] | 926 | 6371.7646 | 104.453 | 627.6076
[12 empty] | 927 | 7322.7777 | 107.2678 | 846.2597
[12 empty] | 928 | 6708.5102 | 104.101 | 625.5916
[12 empty] | 929 | 6535.8593 | 114.7834 | 671.1313
[12 empty] | 930 | 5913.2345 | 95.5887 | 708.9386
[12 empty] | 931 | 5049.3093 | 80.6351 | 799.8276
[12 empty] | 932 | 5465.5727 | 114.5865 | 724.0713
[12 empty] | 933 | 6010.3825 | 119.028 | 655.6867
[12 empty] | 934 | 5916.0068 | 112.1125 | 781.031
[12 empty] | 935 | 5792.1594 | 102.4772 | 842.7968
[12 empty] | 936 | 7670.8458 | 87.0127 | 572.0843
[12 empty] | 937 | 6589.9404 | 83.061 | 550.7348
[12 empty] | 938 | 6680.8485 | 98.3807 | 727.3442
[12 empty] | 939 | 5890.3833 | 92.4103 | 735.3802
[12 empty] | 940 | 5753.3518 | 105.6649 | 1031.966
[12 empty] | 941 | 4968.6342 | 113.0484 | 569.0464
[12 empty] | 942 | 5199.5623 | 86.8193 | 884.1411
[12 empty] | 943 | 5298.2991 | 88.8766 | 832.5414
[12 empty] | 944 | 5185.5317 | 91.792 | 742.0945
[12 empty] | 945 | 4489.5639 | 93.1652 | 748.1825
[12 empty] | 946 | 6174.9787 | 105.346 | 597.8813
[12 empty] | 947 | 4863.9406 | 114.6407 | 886.1286
[12 empty] | 948 | 7951.7901 | 87.1184 | 681.0899
[12 empty] | 949 | 6342.5597 | 74.603 | 562.4412
[12 empty] | 950 | 6344.6739 | 116.347 | 478.4985
[12 empty] | 951 | 7711.901 | 89.4865 | 806.7848
[12 empty] | 952 | 5378.2231 | 94.0853 | 785.0946
[12 empty] | 953 | 5081.3834 | 82.5815 | 670.0747
[12 empty] | 954 | 5988.5143 | 101.8847 | 831.6394
[12 empty] | 955 | 6084.6933 | 106.9143 | 787.5816
[12 empty] | 956 | 6505.404 | 90.7013 | 796.185
[12 empty] | 957 | 5797.9602 | 96.7975 | 862.3544
[12 empty] | 958 | 7242.1634 | 99.7047 | 794.5437
[12 empty] | 959 | 5864.7067 | 119.1896 | 751.9544
[12 empty] | 960 | 5853.5096 | 99.5257 | 706.8025
[12 empty] | 961 | 6324.2202 | 77.3291 | 796.5647
[12 empty] | 962 | 6237.911 | 100.1887 | 721.6088
[12 empty] | 963 | 5274.8248 | 120.8057 | 822.3195
[12 empty] | 964 | 6279.6191 | 106.2433 | 903.4727
[12 empty] | 965 | 6114.1605 | 103.4569 | 699.0607
[12 empty] | 966 | 6037.2582 | 107.2313 | 514.6064
[12 empty] | 967 | 5862.1861 | 105.5087 | 648.7711
[12 empty] | 968 | 5014.7578 | 99.3039 | 835.5212
[12 empty] | 969 | 5460.9332 | 76.5303 | 747.31
[12 empty] | 970 | 6922.8919 | 102.3777 | 541.4471
[12 empty] | 971 | 5449.6889 | 74.782 | 765.071
[12 empty] | 972 | 6420.6245 | 97.1957 | 788.1934
[12 empty] | 973 | 6232.0967 | 85.0883 | 733.5458
[12 empty] | 974 | 6103.2368 | 95.625 | 670.0432
[12 empty] | 975 | 6544.1769 | 110.2778 | 769.0393
[12 empty] | 976 | 7189.7089 | 99.3095 | 797.9339
[12 empty] | 977 | 6864.414 | 103.375 | 663.7755
[12 empty] | 978 | 5783.5851 | 110.0013 | 646.504
[12 empty] | 979 | 6329.4872 | 67.9467 | 772.6938
[12 empty] | 980 | 6988.21 | 109.0379 | 882.9735
[12 empty] | 981 | 5783.5479 | 98.9296 | 747.6611
[12 empty] | 982 | 6183.5641 | 116.1315 | 700.5937
[12 empty] | 983 | 6725.5001 | 89.2042 | 723.7963
[12 empty] | 984 | 6558.2549 | 110.2951 | 742.984
[12 empty] | 985 | 5168.7249 | 111.4635 | 669.1209
[12 empty] | 986 | 7523.7514 | 103.3733 | 511.5725
[12 empty] | 987 | 6150.645 | 104.2833 | 686.8343
[12 empty] | 988 | 5594.2678 | 99.2419 | 762.0274
[12 empty] | 989 | 6795.4805 | 118.1428 | 601.5541
[12 empty] | 990 | 5074.3153 | 94.6231 | 717.0407
[12 empty] | 991 | 6232.5728 | 77.8781 | 687.4429
[12 empty] | 992 | 5705.6492 | 118.2023 | 604.0671
[12 empty] | 993 | 6211.5524 | 92.8214 | 492.2577
[12 empty] | 994 | 6663.1531 | 112.2711 | 642.5191
[12 empty] | 995 | 5210.7153 | 112.9619 | 914.5005
[12 empty] | 996 | 6005.29 | 83.9165 | 696.0347
[12 empty] | 997 | 5034.4997 | 91.3046 | 875.7751
[12 empty] | 998 | 5811.9981 | 86.3718 | 757.7499
[12 empty] | 999 | 7343.3033 | 112.4039 | 634.7737
[12 empty] | 1000 | 6180.078 | 100.3409 | 919.6057
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.